**PLEASANT VALLEY RECREATION AND PARK DISTRICT**

**CONTRACT DOCUMENTS**

**SPECIFICATIONS AND STANDARD DRAWINGS**

**PV POOL DECK RESURFACING PROJECT**

**FISCAL YEAR 2023-2024**

**SPEC NO. PVPD23-24**

**A logo for a recreation and park district

Description automatically generated**

**BID PROPOSALS DUE: TUESDAY, FEBRUARY 9, 2024, AT 10:00 A.M.**

1605 E. Burnley Street  
Camarillo, CA 93010

Phone: (805) 482-1996 / Fax: (805) 482-3468

PLEASANT VALLEY RECREATION & PARK DISTRICT

CONTRACT DOCUMENTS,

SPECIFICATIONS AND STANDARD DRAWINGS

FOR THE

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**FISCAL YEAR 2023-2024**

IN THE CITY OF CAMARILLO, CALIFORNIA

Approved by:

Nick Marienthal, Park Supervisor Date 12/12/2023 \_\_\_\_\_\_\_\_\_\_\_

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**FISCAL YEAR 2023-2024**

**TABLE OF CONTENTS**

TABLE OF CONTENTS i

NOTICE INVITING SEALED BIDS A-1 - A-4

INSTRUCTIONS TO BIDDERS B-1 - B-6

BID FORM C-1 - C-5

BID BOND D-1 - D-2

INFORMATION REQUIRED OF BIDDERS E-1 - E-8

AGREEMENT F-1 - F-4

FAITHFUL PERFORMANCE BOND G-1

LABOR AND MATERIAL BOND H-1 - H-2

WORKERS’ COMPENSATION CERTIFICATE I-1

APPRENTICESHIP REQUIREMENTS J-1

GENERAL PROVISIONS GP-1 - GP-6

SPECIAL PROVISIONS SP-1 - SP-23

TECHNICAL SPECIFICATIONS TP-1 – TP- 6

CONSTRUCTION DRAWINGS APPENDIX A

i

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**NOTICE INVITING SEALED BIDS**

**FOR THE**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**PUBLIC NOTICE IS HEREBY GIVEN THAT:**

Sealed bids will be received at the Office of the Pleasant Valley Recreation and Park District, 1605 E. Burnley Street Camarillo, CA 93010, up to the hour of **10:00 A.M. Tuesday, February 9, 2024,** at which time they will be publicly opened and read aloud in the **Conference Room, 1605 E. Burnley Street, Camarillo, California**, for performing the following work:

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

All in accordance with the plans, specifications, and other contract documents on file in the Parks Department of the Pleasant Valley Recreation & Park District.

The words **“****PV POOL DECK RESURFACING PROJECT, SPEC. NO. PVPD23-24**”shall appear on the envelope of each sealed bid, and each sealed envelope shall be addressed to the Park Supervisor, Nick Marienthal, 1605 E. Burnley Street, Camarillo, CA 93010.

**MANDATORY INFORMATIONAL PRE-BID MEETING.** There will be a Mandatory Informational Pre-Bid meeting **Wednesday, January 24, 2024, at 2:00 P.M., at the Pleasant Valley Aquatic Center, 1030 Temple Avenue, Camarillo, CA 93010.**

**DESCRIPTION OF WORK:** The work to be done consists of furnishing all materials, equipment, tools, labor, and incidentals as required in the Plans, Specifications and Contract documents for said project to complete. The work will take place at 1030 Temple Avenue in Camarillo, California, and other related work as described in the Specifications and Contract Documents, by reference, made a part hereof. **This project is subject to compliance monitoring and enforcement by the Department of Industrial Relations.**

**THE ENGINEER’S ESTIMATE FOR THIS PROJECT IS: $ N/A.**

**COMPLETION OF WORK:** All work to be done under this contract shall be completed within **fifteen (15) consecutive working days, exclusive of maintenance periods,** beginning on the date stipulated in the written "Notice to Proceed" to be issued by the Engineer.

**LIQUIDATED DAMAGES:** Liquidated damages of $250/day will apply to this project. See Special Provisions for detailed information on liquidated damages.

**OBTAINING CONTRACT DOCUMENTS:** Plans, Specifications, and contract documents may be obtained on the District’s website at: <https://www.pvrpd.org/request-for-proposals-bids>. Paper copies are also available in Parks Department, 1605 E. Burnley Street  
Camarillo, CA 93010, (805) 482-1996, upon payment of a $30.00 non-refundable fee if picked up, or payment of a $50.00 non-refundable fee, if mailed. If a FedEx number is provided or alternative shipping fees are paid, the District will send the documents for the pickup price.

**STATE LABOR STANDARDS & WAGE REQUIREMENTS:** In entering into a public works contract, or a subcontract, to supply goods, services, or materials pursuant to a public works contract, the Contractor and all subcontractors agree to follow the State Labor standards. State Labor standards provisions, including prevailing wage requirements, will be enforced such that the general rate of per diem wages (prevailing wage) shall be paid for each craft, classification, or type of worker needed to execute the contract to all workers employed in the execution of the contract. All contractors and subcontractors must furnish electronic certified payroll records directly to the Labor Commissioner (aka Division of Labor Standards Enforcement) as further described in Article IX of the Agreement. The State General Prevailing Wage Determination is as established by the California Department of Industrial Relations (available at <http://www.dir.ca.gov/DLSR/PWD/index.htm>). The prevailing rate of per diem wages are on file at the Pleasant Valley Recreation & Park District, Department of Parks, 1605 E. Burnley Street, Camarillo, CA 93010, and are available to any interested party on request.

**AWARD OF CONTRACT:** Each contractor and subcontractor listed on the bid must be registered with the Department of Industrial Relations pursuant to Labor Code Section 1725.5, subject to the limited exceptions set forth in Labor Code Section 1771.1(a) (regarding the submission of a bid as authorized by Business & Professions Code Section 7029.1 or Public Contract Code [Section 10164 or 20103.5](https://advance.lexis.com/document/?pdmfid=1000516&crid=2d876df3-82c0-4971-980f-04c936b6efde&pddocfullpath=%2Fshared%2Fdocument%2Fstatutes-legislation%2Furn%3AcontentItem%3A5CK9-2GK0-R03K-F2Y7-00000-00&pddocid=urn%3AcontentItem%3A5CK9-2GK0-R03K-F2Y7-00000-00&pdcontentcomponentid=4867&ecomp=8hyg&earg=sr0&prid=5937e7e5-a6ed-42a0-93a2-422744db43fb), provided the contractor is registered to perform public work pursuant to Section 1725.5 at the time the contract is awarded).

**SUBCONTRACTOR'S LIST:** Bidder understands that if he or she fails to specify a subcontractor for any portion of the work to be performed under the contract, he or she shall be deemed to have agreed to perform such portion himself and that he or she shall not be permitted to sublet or subcontract that portion of the work except in cases of public emergency or necessity. In compliance with the provisions of Section 4100 through 4107 of the Public Contract Code of the State of the California and any amendments thereto, the undersigned bidder has set forth on the form provided therefor, the name and location of the place of business of each subcontractor who will perform work or labor or render services to the prime contractor, in or about the construction of or improvements to be performed, under the contract documents to which the attached bid is responsive including special fabrication and installation, and the portion of the work which will be done by each subcontractor for each subcontract in excess of one-half of one percent (1/2%) of this total bid or, in the case of bids for the construction of street and highways, including bridges, in excess of one-half of one percent (1/2%) of this total bid or $10,000.00, whichever is greater. Additionally, once a subcontractor has been listed in the bid, another subcontractor may not be substituted unless the appropriate statutory procedure is followed and the District consents to the substitution.

**BID GUARANTY:** Bids must be accompanied by cash, or by cashier's or certified check made payable to the Pleasant Valley Recreation & Park District, or by a **bid bond** executed by an admitted surety insurer on the bond form provided herein, in the amount of **ten percent (10%)** of the amount of bid price, made payable to the Pleasant Valley Recreation & Park District as a guarantee that the bidder, whose bid is accepted, will promptly execute the contract, secure payment of workers’ compensation insurance, and furnish a satisfactory **faithful performance bond** in the amount of **one hundred percent (100%)** of the total bid price and a **payment bond** (labor and material bond) in the amount of **one hundred percent (100%)** of the total bid price which complies with all of the requirements of Civil Code Section 9554.

**RETENTION:** The District will deduct a five percent (5%) retention from all progress payments as specified in Section 7-3.2 of the 2021 Standard Specifications for Public Works Construction. The District in accordance with Public Contract Code Sect. 22300 shall permit the substitution of securities for any monies withheld by a public agency to ensure performance under a contract. The District hereby incorporates herein all of the provisions set forth in Public Contract Code Sect. 22300.

**CONTRACTOR'S LICENSE:** At the time of “Award of the Contract”, the Prime Contractor must have a valid California State Contractor's License with a classification of **“A”** in accordance with provisions of California Business and Professions Code Sections 7000 through 7145 and the contractor shall warrant that it and all subcontractors are properly licensed, which includes each entity having a local business license.

**DISTRICT'S RIGHTS RESERVED:** The District reserves the right to reject any and all bids or to waive any irregularities or informalities in any bids or in the bidding, should it deem this necessary for the public good, and also the bid of the bidder who has been delinquent or unfaithful in any former contract with the Pleasant Valley Recreation & Park District. No bidder may withdraw his or her bid for a period of **sixty (60) days** after the date from the opening thereof.

**BID REGISTRATION: N/A** Only registered plan holders will be permitted to submit a bid for the project. To register to bid on this project, email the \_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_\_\_\_\_\_\_, at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 72 hours prior to bids being due with the following information: Name of company, company address, name of contact, phone number, fax number, and contact’s email address. The subject line of the email must state: **BID REGISTRATION FOR \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ PROJECT, SPEC NO. \_\_\_\_\_.**

**BID QUESTIONS**: All bid questions shall be submitted by email to Nick Marienthal, at [nmarienthal@pvrpd.org](mailto:nmarienthal@pvrpd.org) for the benefit of all proposed bidders. The questions shall be submitted no later than February 2, 2024, by 5:00 pm for a response.

**BID RESULTS:** Bid results shall also be available on the Pleasant Valley Recreation & Park District’s website ([http://www.](http://www.pvrpd.org)pvrpd.org/) within 24 hours after bid opening.

**INSTRUCTIONS TO BIDDERS**

**BID REGISTRATION: N/A** Only registered plan holders will be permitted to submit a bid for the project. To register to bid on this project, email \_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, at \_\_\_\_\_\_\_\_\_\_\_ at least 72 hours prior to bids being due with the following information: Name of company, company address, name of contact, phone number, fax number, and contact’s email address. The subject line of the email must state: **BID REGISTRATION FOR \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ PROJECT, SPEC NO. \_\_\_\_\_**.

**BID FORM:** All bids shall be submitted on the Bid Forms provided herein for the **PV POOL DECK RESURFACING PROJECT, SPEC NO. PVPD23-24.** All information requested therein must be clearly and legibly set forth in the manner and form indicated. The District will not consider any bid not meeting these requirements.

**DELIVERY OF BIDS:** The bids shall be delivered by the time and to the place stipulated in the "Notice Inviting Sealed Bids.” It is the bidder's sole responsibility to see that his or her bid is received at the proper time. Any bid received after the scheduled closing time for receipt of bids will be returned to the bidder unopened. Bidders or their authorized agents are invited to be present at bid opening.

**MODIFICATIONS AND ALTERNATIVE BIDS:** Unauthorized conditions, limitations, or provisos attached to a bid will render it unresponsive and may cause its rejection. The complete bid forms shall be without alterations or erasures, unless each such correction is suitably authenticated by affixing in the margin immediately opposite the correction the surname or surnames of the person or persons signing the bid. Alternative bids will not be considered unless called for. No oral, telegraphic, or telephonic bid or modifications will be considered.

**WITHDRAWAL OF BID:** The bid may be withdrawn upon request by the bidder without prejudice to himself prior to, but not after the time fixed for opening of bids, provided that the request is in writing, has been executed by the bidder or his or her duly authorized representative, and is filed with the Clerk of the Board. **No bid may be withdrawn during the period of sixty (60) days after the opening of bids.**

**BID GUARANTY:** Each bid shall be accompanied by cash, or a cashier's or certified check, or by a bid bond in the amount of **ten percent (10%)** of the amount named in the bid. Said check or bond shall be made payable to the District and shall be given as a guarantee that the bidder, if awarded the work, will enter into a contract within fifteen (15) days after written notice of the award and will furnish the necessary bonds as hereinafter provided. In case of refusal or failure to enter into said contract, the check or bond, as the case may be, shall be forfeited to the District. No bidder's bond will be accepted unless it conforms substantially to the form furnished by the District, which is bound herein, and is properly filled out and executed.

**DISCREPANCIES IN BIDS:** In case of discrepancy between numeric and handwritten amounts, the handwritten amount shall prevail. In case of discrepancy between the unit cost and the total set forth for that item, the unit cost shall prevail, provided however, if the amount set forth as a unit cost is ambiguous, unintelligible, or uncertain for any cause, or if is omitted, or in the case of unit basis items, is the same amount as the entry in the "Total Item Amount" column, then the amount set forth in the "Total Item Amount" column for the item shall prevail in accordance with the following:

(1) As to lump sum items, the amount set forth in the "Total Item Amount" column shall be the item price.

(2) As to unit basis items, the amount set forth in the "Total Item Amount" column shall be divided by the estimated quantity for the item and the price thus obtained shall be the unit costs.

If the "Total Contract Amount" does not equal the sum of the item totals, then the Engineer, after resolving any discrepancy in the item price totals, shall sum the total column and the resultant amount shall be considered the "Total Contract Amount".

**COMPETENCY OF BIDDERS:** In selecting the lowest responsible bidder, consideration will be given not only to the financial standing but also to the general competency of the bidder for the performance of the work covered by the plans and specifications. To this end, each bid shall be supported by a statement of the bidder's experience on the form entitled **"Information Required of Bidder"** bound herein. No bid will be awarded to a Contractor who, at the time of the bid opening and “Award of the Contract”, is not licensed in accordance with the laws of the State of California under applicable provisions of the Business and Professions Code or from a Contractor who has failed to demonstrate the attributes of trustworthiness, quality, fitness, capacity and experience to satisfactorily perform the public works contract. The Contractor shall include the Contractor's license number, license classification, and license expiration date on the form furnished herein entitled "Information Required of Bidders.” The licensing requirements for Contractors shall apply also to Subcontractors. In addition, any contractor or subcontractor who is ineligible under [Lab C §§1777.1](http://online.ceb.com/CalCodes/code.asp?code=LAB&section=1777.1) and [1777.7](http://online.ceb.com/CalCodes/code.asp?code=LAB&section=1777.7) is prohibited from working on this Project.

**SUBCONTRACTOR'S LIST:** Bidder understands that if he or she fails to specify a subcontractor for any portion of the work to be performed under the contract, he or she shall be deemed to have agreed to perform such portion himself and that he or she shall not be permitted to sublet or subcontract that portion of the work except in cases of public emergency or necessity. In compliance with the provisions of Section 4100 through 4107 of the Public Contract Code of the State of the California and any amendments thereto, the undersigned bidder has set forth on the form provided therefor, the name and location of the place of business of each subcontractor who will perform work or labor or render services to the prime contractor, in or about the construction of or improvements to be performed, under the contract documents to which the attached bid is responsive including special fabrication and installation, and the portion of the work which will be done by each subcontractor for each subcontract in excess of one-half of one percent (1/2%) of this total bid or, in the case of bids for the construction of street and highways, including bridges, in excess of one-half of one percent (1/2%) of this total bid or $10,000.00, whichever is greater. Additionally, once a subcontractor has been listed in the bid, another subcontractor may not be substituted unless the appropriate statutory procedure is followed and the District consents to the substitution.

**BIDDER'S EXAMINATION OF SITE:** Each bidder shall carefully examine the site of the proposed work and the contract documents herein. It will be assumed that the bidder has investigated and is satisfied as to the conditions to be encountered; as to the character, quality, and quantity of the materials to be furnished; and as to the requirements of the contract, specifications, and drawings. The name of the individual who examined the site of the work and the date of such examination shall be stated in the form entitled "Information Required of Bidder" in the space provided therefor.

**EQUIVALENT MATERIALS:** Approval of equipment and materials offered as equivalents to those specified must be obtained in writing from the District. Requests for consideration of equivalents must be submitted in writing allowing five (5) working days for complete consideration of all specifications, samples, references, tests, and other details to the full satisfaction of the District.

**TAXES:** No mention shall be made in the bid of Sales Tax, Use Tax, or any other tax, as all amounts bid will be deemed and held to include any such taxes that may be applicable.

**DISQUALIFICATION OF BIDDERS:** More than one bid from an individual, firm partnership, corporation, or association under the same or different names will not be considered. Reasonable grounds for believing that any bidder is interested in more than one bid for the work contemplated will cause the rejection of all bids in which such bidder is interested. If there is reason for believing that collusion exists among the bidders, all bids will be rejected and none of the participants in such collusion will be considered in future bids. Similarly, failure to comply with the registration requirements of Labor Code Section 1725.5, as further described in the Notice Inviting Bidders, will disqualify a Bidder.

**RETURN OF BID GUARANTIES:** Within **ten (10) days** after award of the contract, the District will return the bid guaranties made by check accompanying each of the bids except for the three (3) lowest bidders. All other bid guaranties made by check will be held until the contract has been finally executed. They will then be returned to the respective bidders whose bids they accompany. Bid guaranties made by bond shall be void according to the bid bond language, page D-1.

**AWARD OF CONTRACT:** Bids will be compared on the basis of the lowest possible cost and the contract, if awarded, will be awarded to a responsible bidder whose bid complies with the requirements of these specifications. The award, if made, will be made within **sixty (60) days** after the opening of the bids, provided that the award may be made after said period if the successful bidder shall not have given the District written notice of the withdrawal of his or her bid.

**EXECUTION OF CONTRACT:** The bidder to whom award is made shall execute a written contract with the District on the form agreement provided and shall secure all insurance and bonds as herein provided within **fifteen (15) days** from the date of written notice of the award. Failure or refusal to enter into a contract as herein provided, or to conform to any of the stipulated requirements in connection therewith shall be just cause for the annulment of the award and the forfeiture of the bid guaranty.

If the successful bidder refuses or fails to execute the contract, the District may award the contract to the second lowest responsible bidder. If the second lowest responsible bidder refuses or fails to execute the contract, the District may award the contract to the third lowest responsible bidder. On the failure or refusal of such second or third lowest bidder to execute the contract, such bidder's guaranty shall be likewise forfeited to the District. The work may then be re-advertised.

**INSURANCE:** **Certificates in the amounts required shall be furnished by the Contractor to the District and approved by the District prior to the commencement of work.**

The Contractor and its subcontractors shall maintain insurance in conformance with the requirements set forth below. Contractor will use existing coverage to comply with these requirements. If that existing coverage does not meet the requirements set forth herein, Contractor agrees to amend, supplement, or endorse the existing coverage to do so.

Contractor acknowledges that the insurance coverage and policy limits set forth in this section constitute the minimum amount of coverage required. Any insurance proceeds available to Contractor or its subcontractors in excess of the limits and coverage identified in this Agreement and which is applicable to a given loss, claim or demand, will be equally available to District.

Contractor shall provide the following types and amounts of insurance:

Without limiting Contractor’s indemnification of District, and prior to commencement of Work, Contractor shall obtain, provide, and maintain at its own expense during the term of this Agreement, policies of insurance of the type and amounts described below and in a form satisfactory to District:

**General liability insurance.** Contractor shall maintain commercial general liability insurance with coverage at least as broad as Insurance Services Office form CG 00 01, in an amount not less than $5,000,000 per occurrence, $10,000,000 general aggregate on an “occurrence” basis, for bodily injury, personal injury, and property damage, and a $10,000,000 completed operations aggregate. The policy must include contractual liability that has not been amended. Any endorsement restricting standard ISO “insured contract” language will not be accepted.

**Automobile liability insurance.** Contractor shall maintain automobile insurance at least as broad as Insurance Services Office form CA 00 01 covering bodily injury and property damage for all activities of the Contractor arising out of or in connection with Work to be performed under this Agreement, including coverage for any owned, hired, non-owned or rented vehicles, in an amount not less than $5,000,000 combined single limit for each accident.

**Umbrella or excess liability insurance.** Contractor shall obtain and maintain an umbrella or excess liability insurance that will provide bodily injury, personal injury and property damage liability coverage at least as broad as the primary coverages set forth above, including commercial general liability and employer’s liability. Such policy or policies shall include the following terms and conditions:

* A drop-down feature requiring the policy to respond in the event that any primary insurance that would otherwise have applied proves to be uncollectable in whole or in part for any reason; and
* Pay on behalf of wording as opposed to reimbursement; and
* Concurrency of effective dates with primary policies; and
* Policies shall “follow form” to the underlying primary policies; and
* Insureds under primary policies shall also be insureds under the umbrella or excess policies.

**Workers’ compensation insurance.** Contractor shall maintain Workers’ Compensation Insurance (Statutory Limits) and Employer’s Liability Insurance (with limits of at least $1,000,000) for Contractor’s employees in accordance with the laws of the State of California, Section 3700 of the Labor Code. In addition, Contractor shall require each subcontractor to similarly maintain Workers’ Compensation Insurance and Employer’s Liability Insurance in accordance with the laws of the State of California, Section 3700 for all of the subcontractor’s employees.

Contractor shall submit to District, along with the certificate of insurance, a Waiver of Subrogation endorsement in favor of District, its officers, agents, employees and volunteers.

**Pollution liability insurance.** Environmental Impairment Liability Insurance shall be written on a Contractor’s Pollution Liability form or other form acceptable to District providing coverage for liability arising out of sudden, accidental, and gradual pollution and remediation. The policy limit shall be no less than $1,000,000 dollars per occurrence or claim, and $2,000,000 policy aggregate. All activities contemplated in this Agreement shall be specifically scheduled on the policy as “covered operations.” The policy shall provide coverage for the hauling of waste from the project site to the final disposal location, including non-owned disposal sites.

Products/completed operations coverage shall extend a minimum of three (3) years after project completion. Coverage shall be included on behalf of the insured for covered claims arising out of the actions of independent contractors. If the insured is using subcontractors, the Policy must include work performed “by or on behalf” of the insured. Policy shall contain no language that would invalidate or remove the insurer’s duty to defend or indemnify for claims or suits expressly excluded from coverage. Policy shall specifically provide for a duty to defend on the part of the insurer. The District, its officials, officers, agents, and employees, shall be included as insureds under the policy.

**Builder’s risk insurance**. Upon commencement of construction and with approval of District, Contractor shall obtain and maintain builder’s risk insurance for the entire duration of the project until only the District has an insurable interest. The Builder’s Risk coverage shall include the coverages as specified below.

The named insureds shall be Contractor and District, including its officers, officials, employees, and agents. All subcontractors (excluding those solely responsible for design Work) of any tier and suppliers shall be included as additional insureds as their interests may appear. Contractor shall not be required to maintain property insurance for any portion of the project following transfer of control thereof to District. The policy shall contain a provision that all proceeds from the builder’s risk policy shall be made payable to the District. The District will act as a fiduciary for all other interests in the project.

The policy shall be provided for replacement value on an "all risk" basis for the completed value of the project. There shall be no coinsurance penalty or provisional limit provision in any such policy. The policy must include: (1) coverage for any ensuing loss from faulty workmanship, Nonconforming Work, omission or deficiency in design or specifications; (2) coverage against machinery accidents and operational testing; (3) coverage for removal of debris, and insuring the buildings, structures, machinery, equipment, materials, facilities, fixtures and all other properties constituting a part of the project; (4) Ordinance or law coverage for contingent rebuilding, demolition, and increased costs of construction; (5) transit coverage (unless insured by the supplier or receiving contractor), with sub-limits sufficient to insure the full replacement value of any key equipment item; (6) Ocean marine cargo coverage insuring any project materials or supplies, if applicable; (7) coverage with sub-limits sufficient to insure the full replacement value of any property or equipment stored either on or off the Site or any staging area. Such insurance shall be on a form acceptable to District to ensure adequacy of terms and sub-limits and shall be submitted to the District prior to commencement of construction.

**Other Provisions or Requirements**

**Proof of insurance.** Contractor shall provide certificates of insurance to District as evidence of the insurance coverage required herein, along with a waiver of subrogation endorsement for workers’ compensation. Insurance certificates and endorsements must be approved by District’s risk manager prior to commencement of performance. Current certification of insurance shall be kept on file with District at all times during the term of this contract. District reserves the right to require complete, certified copies of all required insurance policies, at any time.

**Duration of coverage.** Contractor shall procure and maintain for the duration of the contract insurance against claims for injuries to persons or damages to property, which may arise from or in connection with the performance of the Work hereunder by Contractor, his agents, representatives, employees or subcontractors. Contractor must maintain general liability and umbrella or excess liability insurance for as long as there is a statutory exposure to completed operations claims. District and its officers, officials, employees, and agents shall continue as additional insureds under such policies.

**Primary/noncontributing.** Coverage provided by Contractor shall be primary and any insurance or self-insurance procured or maintained by District shall not be required to contribute with it. The limits of insurance required herein may be satisfied by a combination of primary and umbrella or excess insurance. Any umbrella or excess insurance shall contain or be endorsed to contain a provision that such coverage shall also apply on a primary and non-contributory basis for the benefit of District before the District’s own insurance or self-insurance shall be called upon to protect it as a named insured.

**District’s rights of enforcement.** In the event any policy of insurance required under this Agreement does not comply with these requirements or is canceled and not replaced, District has the right but not the duty to obtain the insurance it deems necessary, and any premium paid by District will be promptly reimbursed by Contractor or District will withhold amounts sufficient to pay premium from Contractor payments. In the alternative, District may cancel this Agreement.

**Acceptable insurers.** All insurance policies shall be issued by an insurance company currently authorized by the Insurance Commissioner to transact business of insurance or is on the List of Approved Surplus Line Insurers in the State of California, with an assigned policyholders’ Rating of A- (or higher) and Financial Size Category Class VII (or larger) in accordance with the latest edition of Best’s Key Rating Guide, unless otherwise approved by the District’s risk manager.

**Waiver of subrogation.** All insurance coverage maintained or procured pursuant to this agreement shall be endorsed to waive subrogation against District, its elected or appointed officers, agents, officials, employees and volunteers or shall specifically allow Contractor or others providing insurance evidence in compliance with these specifications to waive their right of recovery prior to a loss. Contractor hereby waives its own right of recovery against District and shall require similar written express waivers and insurance clauses from each of its subconsultants.

**Enforcement of contract provisions (non estoppel).** Contractor acknowledges and agrees that any actual or alleged failure on the part of the District to inform Contractor of non-compliance with any requirement imposes no additional obligations on the District nor does it waive any rights hereunder.

**Requirements not limiting.** Requirements of specific coverage features or limits contained in this Section are not intended as a limitation on coverage, limits or other requirements, or a waiver of any coverage normally provided by any insurance. Specific reference to a given coverage feature is for purposes of clarification only as it pertains to a given issue and is not intended by any party or insured to be all inclusive, or to the exclusion of other coverage, or a waiver of any type. If the Contractor maintains higher limits than the minimums shown above, the District requires and shall be entitled to coverage for the higher limits maintained by the Contractor. Any available insurance proceeds in excess of the specified minimum limits of insurance and coverage shall be available to the District.

**Notice of cancellation.** Contractor agrees to oblige its insurance agent or broker and insurers to provide to District with a thirty (30) day notice of cancellation (except for nonpayment for which a ten (10) day notice is required) or nonrenewal of coverage for each required coverage.

**Additional insured status**. General liability policies shall provide or be endorsed to provide that District and its officers, officials, employees, agents, and volunteers shall be additional insureds under such policies. This provision shall also apply to any excess/umbrella liability policies.

**Prohibition of undisclosed coverage limitations.** None of the coverages required herein will be in compliance with these requirements if they include any limiting endorsement of any kind that has not been first submitted to District and approved of in writing.

**Separation of insureds.** A severability of interests provision must apply for all additional insureds ensuring that Contractor’s insurance shall apply separately to each insured against whom claim is made or suit is brought, except with respect to the insurer’s limits of liability. The policy(ies) shall not contain any cross-liability exclusions.

**Pass through clause.** Contractor agrees to ensure that its subconsultants, subcontractors, and any other party involved with the project who is brought onto or involved in the project by Contractor, provide the same minimum insurance coverage and endorsements required of Contractor. Contractor agrees to monitor and review all such coverage and assumes all responsibility for ensuring that such coverage is provided in conformity with the requirements of this section. Contractor agrees that upon request, all agreements with consultants, subcontractors, and others engaged in the project will be submitted to District for review.

**Agency’s right to revise requirements.** The District reserves the right at any time during the term of the contract to change the amounts and types of insurance required by giving the Contractor a ninety (90) day advance written notice of such change. If such change results in substantial additional cost to the Contractor, the District and Contractor may renegotiate Contractor’s compensation.

**Self-insured retentions.** Any self-insured retentions must be declared to and approved by District. District reserves the right to require that self-insured retentions be eliminated, lowered, or replaced by a deductible. Self-insurance will not be considered to comply with these specifications unless approved by District.

**Timely notice of claims.** Contractor shall give District prompt and timely notice of claims made or suits instituted that arise out of or result from Contractor’s performance under this Agreement, and that involve or may involve coverage under any of the required liability policies.

**Additional insurance**. Contractor shall also procure and maintain, at its own cost and expense, any additional kinds of insurance, which in its own judgment may be necessary for its proper protection and prosecution of the Work.

**BONDS:** **The required bonds in the amounts required shall be furnished by the Contractor to the District and approved by the District prior to the commencement and throughout the duration of the work.**

The Contractor shall secure with a responsible corporate surety or corporate sureties, satisfactory bonds conditioned upon faithful performance by the Contractor, of all requirements under the contract and upon the payment of claims of material supplier and laborers thereunder. The **Faithful Performance Bond** shall be in the sum of not less than **one hundred percent (100%)** of the estimated aggregate amount of the payments to be made under the contract computed on the basis of the prices stated in the bid. The **Payment Bond** (Labor and Material Bond) shall be in the sum of not less than **one hundred percent (100%)** of the estimated aggregate amount of the payments to be made under the contract computed on the basis of the prices stated in the bid.

The payment bond shall contain the original notarized signature of an authorized officer of the surety and affixed thereto shall be a certified and current copy of his power of attorney. **The payment bond shall be unconditional and remain in force during the entire term of the contract** agreement and shall be null and void only if the Contractor completely and faithfully pays all subcontractors and suppliers.

**SUFFICIENCY OF INSURER OR SURETY FOR PAYMENT BOND AND PERFORMANCE BOND:**  All insurers are to be rated A or better according to the most recent Best Rating Guide or The Key Rating Guide, and only if they are of a financial category Class VII or better, unless such requirements are waived by the Risk Manager of the District due to unique circumstances. All sureties shall be admitted surety insurers authorized to do business in the State of California by the Insurance Commissioner. Should the District object to the sufficiency of the insurer or surety the Contractor shall immediately deliver to the District the following documents:

(a) A copy of the “Certificate of Authority” of the Insurer or Surety issued by the Insurance Commissioner, which authorizes the Insurer or Surety to transact surety insurance in the State of California; or

(b) A certificate from the Clerk of the County of Ventura that the “Certificate of Authority” of the Insurer or Surety has not been surrendered, revoked, canceled, annulled, or suspended or, in the event the “Certificate of Authority” of the Insurer or Surety has been suspended, that renewed authority has been granted.

Failure of Contractor to timely deliver these documents shall require the District to refrain from entering the agreement, as Contractor will be deemed to have failed to ensure the sufficiency of the Insurer or Surety to the satisfaction of the District, as required by the provisions of the Bond and Undertaking Law, Code of Civil Procedure 995.660. Upon receipt of any bonds, District shall contact the bond company to verify the bond’s validity.

**EVIDENCE OF RESPONSIBILITY:** Upon the request of the District, a bidder whose bid is under consideration for the award of the contract shall submit promptly to the District satisfactory evidence showing the bidder's financial resources, his or her construction experience, and his or her organization and plant facilities available for the performance of the contract.

**EMPLOYMENT OF APPRENTICES:** Attention is directed to the provisions in Sections 1777.5 and 1777.6 of the California Labor Code concerning employment of apprentices by the Contractor, or any Subcontractor under the Contractor. The Contractor, and any Subcontractor under the Contractor, shall comply with the requirements of said sections in the employment of apprentices; however, the Contractor shall have full responsibility for compliance with said Labor Code sections for all apprenticeable occupations, regardless of any other contractual or employment relationships alleged to exist.

**WAGE RATES:** In entering into a public works contract, or a subcontract, to supply goods services, or materials pursuant to a public works contract, the Contractor, or subcontractor, offers and agrees to follow the State Labor standards. State Labor standards provisions, including prevailing wage requirements, will be enforced. The State General Prevailing Wage Determination is as established by the California Department of Industrial Relations (available at <http://www.dir.ca.gov/DLSR/PWD/index.htm>). The general rate of per diem wages (prevailing wage) shall be paid for each craft, classification, or type of worker needed to execute the contract to all workers employed in the execution of the contract. The prevailing rate of per diem wages are on file at the Pleasant Valley Recreation & Park District, Department of Parks, 1605 E. Burnley Street, Camarillo, CA 93010, and are available to any interested party on request.

California Labor Code section 1773.3 requires that public agencies notify the DIR when public projects are awarded within 30 days of award and the imposition of a fine at a rate of $100 per day, not to exceed $10,000, was authorized for failure to provide notification. At the time of award, the bidder will be requested to provide DIR Award Notification Data for each General Contractor and for each Sub-contractor performing work on the project which data will be necessary to notify DIR of the award. If the Contractor fails to provide the requested DIR Award Notification Data within 30 days after the issuance of the Notice of Award/Notice to Proceed, thereby causing District to incur the imposition of a fine by the DIR, such fine will be imposed upon the General Contractor for reimbursement.

**SAFETY PERMIT:** The Contractor, and not the District, shall be responsible for performing safety inspections for this project. Particular attention is called to Subsection 7-10.4.1 of the Standard Specifications for Public Works Construction, which requires orders issued by the California Division of Occupational Health and Safety (Cal/OSHA). The Contractor, if needed, shall secure a permit for excavation and trenching from Cal/OSHA and shall file a copy of such permit with the Engineer prior to commencement of work.

**CARB CERTIFICATES**: Before award of contract and for a project involving the use of in-use off-road diesel-fueled vehicles, as defined by 13 CCR 2449, bidder shall obtain and provide to District copies of the valid Certificates of Reported Compliance, as described in 13 CCR 2449(n), for the fleet performing services pursuant to this bid and all listed subcontractors.

**OTHER PERMITS, FEES, AND LICENSES:** The Contractor shall, prior to the start of construction, obtain a **"Construction Permit"** from the District. This will be a **NO FEE Permit**. In addition, the Contractor, and **ALL** sub-contractors, **shall possess a City business license** at the time of application for the Construction Permit and for the duration of the contract. The amount of the business license fee may be obtained from the City of Camarillo.

**BID FORM**

**FIRM NAME:**

**POINT OF CONTACT:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**ADDRESS:**

**TELEPHONE NUMBER:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**FAX NUMBER:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**FOR THE**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**FISCAL YEAR 2023-2024**

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**BID FOR THE**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

TO THE PLEASANT VALLEY RECREATION & PARK DISTRICT:

This Bid is submitted in accordance with the advertised “Notice Inviting Sealed Bids” to perform all work and improvements therein described, and to furnish all labor and materials, equipment and incident insurance necessary therefor, in accordance with the specifications therefor known as “**PV POOL DECK RESURFACING PROJECT, SPEC NO. PVPD23-24”** which are on file in the office of the Parks of the Pleasant Valley Recreation & Park District.

Definition of Terms (for a complete definition of terms, see Standard Specifications for Public Works Construction, 2021 Edition):

CY Cubic yard

EA Each

LF Linear foot

LS Lump sum

SF Square foot

SY Square yard

TON Ton

The undersigned Bidder hereby proposes and agrees to enter into a contract to perform the work and improvements therein mentioned to the satisfaction of and under the supervision of the Parks of the Pleasant Valley Recreation & Park District, duly appointed for said work in the matter of the construction and installation of **“PV POOL DECK RESURFACING PROJECT, SPEC NO. PVPD23-24”,** for the sum set forth in the following schedule:

NOTE: The estimated quantities shown herein are approximate and to be used only for comparison of bids. Payment for quantities will be made for actual materials used on the job and based on the unit costs shown below. The District reserves the right to increase or decrease the amount of any quantity shown and to delete all or any item from the contract.

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**BID SCHEDULE**

| ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | UNIT COST | TOTAL ITEM AMOUNT | NOTE |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| TOTAL BID AMOUNT IN FIGURES | | | | | $ |  |
| TOTAL BID AMOUNT IN WORDS | | | | | |  |

Bidder Name

Signature of Bidder

Dated

**RESOLUTION OF CONSTRUCTION CLAIMS**

(To Be Executed By Bidder and Submitted With Bid)

When a Public Works claim is made to the District, the District will conduct a reasonable review of the claim and, within 45 days, provide the claimant with a written statement identifying what portion of the claim is disputed and what portion is undisputed and both parties shall work to resolve the claim as by Public Contract Code 9204. (A copy of Section 9204 may be found in the Special Provisions, under “Resolution of Construction Claims”).

Additionally, in all Public Works claims, which may arise between the Contractor and the District which do not exceed the sum of three hundred seventy-five thousand dollars ($375,000), the requirements of California Public Contract Code, Section 20104 through 20104.6, inclusive, shall apply. (A copy of said Code Sections may be found in the Special Provisions, under “Resolution of Construction Claims of $375,000 or Less”.) Said Code Sections shall apply for the purpose of filing claims and civil actions for claims as defined in Section 20104 of the Public Contract Code.

The bidder’s signature is required to verify he/she has reviewed the Code Sections.

Bidder Name

Signature of Bidder

Dated

**BID BOND**

(10% of the Bid Amount)

**KNOW ALL MEN BY THESE PRESENTS** that we \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ as Principal, hereinafter referred to as “Contractor” and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ as Surety, are held and firmly bound unto the Pleasant Valley Recreation & Park District, hereinafter called the “District,” in the sum of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Dollars ($\_\_\_\_\_\_\_\_\_\_\_\_), for the payment of which sum well and truly to be made, we bind ourselves, our heirs, executors, administrators, and successors, jointly and severally, firmly by these presents. The conditions of this obligation are such that whereas the Contractor submitted to the District a certain Bid, attached hereto and hereby made a part hereof, to enter into a contract in writing for the

,

and will furnish all required certificates of insurance and bonds as required by the Contract.

**NOW, THEREFORE**, if said Bid shall be rejected; or in the alternate, if said Bid is accepted, and the Contractor (i) executes and delivers a contract in the prescribed form of the Agreement, (ii) delivers certificates evidencing that the required insurance is in effect, (iii) executes and delivers Performance and Payment Bonds in the forms prescribed, and (iv) in all other respects performs the agreement created by the acceptance of said Bid, then this obligation shall be void; otherwise this obligation shall remain in full force and effect, it being expressly understood and agreed that the liability of the Surety for any and all default of the Contractor hereunder shall be the amount of this obligation as herein stated. In the event suit is brought upon this bond by District and judgment is recovered, Surety shall pay all costs incurred by District in said suit, including a reasonable attorney's fee to be fixed by the court.

The Surety, for the value received, hereby stipulates and agrees that the obligations of said Surety and its bond shall in no way be impaired or affected by an extension of the time within which the District may accept such a bid; and said Surety does hereby waive notice of any such extension.

IN WITNESS WHEREOF, the above-bound parties have executed this instrument under their several seals this \_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 202\_\_, the name and corporate seal of each corporate party being hereto affixed and these presents duly signed by its undersigned representative, pursuant to authority of its governing body.

ATTEST:

(Contractor)

(Address)

(By)

(Title)

ATTEST:

(Surety)

(Address)

(By)

(Title)

(To be filled in by Surety):

The rate of premium on this bond is $\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ per thousand.

The total amount of premium charged is $\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**NOTARY PUBLIC ATTACH CALIFORNIA ALL-PURPOSE ACKNOWLEDGEMENT**

**INFORMATION REQUIRED OF BIDDERS**

**The bidder is required to supply the following information.**

(Additional sheets may be attached if necessary.)

(1) Address:

(2) Telephone: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(3) Type of Firm:

(Individual, Partnership, or Corporation)

(4) Contractor's State License Classification Expiration date

1. Corporate organized under the laws of the State of:
2. Is 51% or more of the business owned by: American Indian ( ), Asian ( ), Black ( ), Hispanic ( ), Female ( ), Other (Specify) .

(7) List the names and addresses of all members of the firm, or names and titles of all officers of the corporation.

(8) Number of years of experience as a Contractor in construction work.

1. List at least three (3) completed similar projects completed in the last 24 months:

Contract Date Name, Contact, Address and

Amount Class of Work Completed Telephone No. of Client

$\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Contract Date Name, Contact, Address and

Amount Class of Work Completed Telephone No. of Client

$\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Contract Date Name, Contact, Address and

Amount Class of Work Completed Telephone No. of Client

$\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(10) List the name of the person who inspected the site of the proposed work for your firm:

Date of Inspection:

(11) If requested by the District, the Bidder shall furnish a notarized financial statement, financial data, or other information and reference sufficiently comprehensive to permit an appraisal of Bidder’s current financial condition.

(12) List the name and address of all **subcontractors who will perform work** in or about the project and indicate what part of the work will be done by each such Subcontractor.

NAME:

ADDRESS:

LICENSE NO. & CLASS:

WORK TO BE PERFORMED:

NAME:

ADDRESS:

LICENSE NO. & CLASS:

WORK TO BE PERFORMED:

NAME:

ADDRESS:

LICENSE NO. & CLASS:

WORK TO BE PERFORMED:

NAME:

ADDRESS:

LICENSE NO. & CLASS:

WORK TO BE PERFORMED:

NAME:

ADDRESS:

LICENSE NO. & CLASS:

WORK TO BE PERFORMED:

List the name and address of **Major Equipment Suppliers** who will provide equipment or major components for the project.

NAME:

ADDRESS:

EQUIPMENT TO BE PROVIDED:

NAME:

ADDRESS:

EQUIPMENT TO BE PROVIDED:

NAME:

ADDRESS:

EQUIPMENT TO BE PROVIDED:

NAME:

ADDRESS:

EQUIPMENT TO BE PROVIDED:

NAME:

ADDRESS:

EQUIPMENT TO BE PROVIDED:

(13) The Contractor shall furnish the following information concerning bid depository or registry services used in obtaining subcontractor bid figures for this Bid. Additional sheets may be attached if necessary.

A. Were bid depository or registry services used in obtaining subcontractor bid figures in order to compute your bid? Yes ( ) No ( )

B. If the answer to “A.” is "Yes,” forward a copy of the rules of each bid depository you used in the preparation of this Bid.

C. Did you have any source of subcontractor bids other than bid depositories?

Yes ( ) No ( )

D. Has any person or group threatened you with subcontractor boycotts, union boycotts, or other sanctions to attempt to convince you to use the services or abide by the rules of one or more bid depositories? Yes ( ) No ( )

E. If the answer to “D” is "Yes", please explain the following details:

1. Date:

(b) Name of person or group:

(c) Job involved (if applicable):

(d) Nature of threats:

1. Additional comments:

**(TO ACCOMPANY BID)**

In accordance with Public Contracting Code Section 10162, the bidder shall complete, under penalty of perjury, the following questionnaire:

**QUESTIONNAIRE**

Has the bidder, any officer of the bidder, or any employee of the bidder who has a proprietary interest in the bidder, ever been disqualified, removed, or otherwise prevented from bidding on or completing a Federal, State, or local government project because of a violation of law or a safety regulation?

Yes \_\_\_\_\_\_ No \_\_\_\_\_\_\_

If the answer is yes, explain the circumstances in the following space:

Note: This questionnaire constitutes a part of the Bid, and a signature on the Bid shall be constituted a signature on this questionnaire.

**CONTRACTOR LICENSE AFFIDAVIT**

**STATE OF CALIFORNIA )**

**COUNTY OF**\_\_\_\_\_\_\_\_\_\_\_**) ss.**

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, being first duly sworn, deposes

**Name**

and says that he or she is \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

**Title** **Name of Firm**

the party making the foregoing bid, is a licensed Contractor, a duly authorized partner of a Joint Venture which holds a license as a Partnership, or a duly authorized principal and/or representative of a Corporation which holds a license as a Corporation, and that he or she understands the information shown below shall be included with the bid, and understands that any bid not containing this information, or if this information is subsequently proven to be false, shall be considered non-responsive and shall be rejected by the Pleasant Valley Recreation & Park District.

**Contractor's State License Number and Classification**

**License Expiration Date**

I certify under penalty of perjury under the laws of the State of California that the foregoing is true and correct.

Subscribed at:

(City and County, State)

on \_ , 20 .

Signature State License Number and Classification

Street Address City State Zip Code

Telephone Number

A notary public or other officer completing this

certificate verifies only the identity of the

individual who signed the document to which this

certificate is attached, and not the truthfulness,

accuracy or validity of that document.

STATE OF CALIFORNIA )

) ss.

COUNTY OF\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ )

On \_\_\_\_\_\_\_\_\_\_\_\_\_, 20\_\_, before me, \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, a Notary Public, personally appeared \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, who proved to me on the basis of satisfactory evidence to be the person(s) whose name(s) is/are subscribed to the within instrument and acknowledged to me that he/she/they executed the same in his/her/their authorized capacity(ies), and that by his/her/their signature(s) on the instrument the person(s), or the entity upon behalf of which the person(s) acted executed the instrument.

I certify under PENALTY OF PERJURY under the laws of the State of California that the foregoing paragraph is true and correct.

WITNESS my hand and official seal.

Signature\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(Seal)

**NONCOLLUSION DECLARATION TO BE EXECUTED**

**BY**

**BIDDER AND SUBMITTED WITH BID**

The undersigned declares:

I am the \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, the party making the foregoing bid.

The bid is not made in the interest of, or on behalf of, any undisclosed person, partnership, company, association, organization, or corporation. The bid is genuine and not collusive or sham. The bidder has not directly or indirectly induced or solicited any other bidder to put in a false or sham bid. The bidder has not directly or indirectly colluded, conspired, connived, or agreed with any bidder or anyone else to put in a sham bid, or to refrain from bidding. The bidder has not in any manner, directly or indirectly, sought by agreement, communication, or conference with anyone to fix the bid price of the bidder or any other bidder, or to fix any overhead, profit, or cost element of the bid price, or of that of any other bidder. All statements contained in the bid are true. The bidder has not, directly or indirectly, submitted his or her bid price or any breakdown thereof, or the contents thereof, or divulged information or data relative thereto, to any corporation, partnership, company, association, organization, bid depository, or to any member or agent thereof, to effectuate a collusive or sham bid, and has not paid, and will not pay, any person or entity for such purpose.

Any person executing this declaration on behalf of a bidder that is a corporation, partnership, joint venture, limited liability company, limited liability partnership, or any other entity, hereby represents that he or she has full power to execute, and does execute, this declaration on behalf of the bidder.

I declare under penalty of perjury under the laws of the State of California that the foregoing is true and correct and that this declaration is executed on \_\_\_\_\_\_\_\_\_\_\_\_ [date], at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [city], \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [state].

**SAMPLE AGREEMENT**

**THIS AGREEMENT,** made and entered into by and between the **PLEASANT VALLEY RECREATION & PARK DISTRICT, CALIFORNIA,** hereinafter referred to as the **"District"** and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_hereinafter referred to as the **"Contractor"**.

**WITNESSETH:** That the parties hereto do mutually agree as follows:

#### ARTICLE I: For and in consideration of the payments and agreements hereinafter mentioned to be made and performed by said District, said Contractor agrees with said District to construct the work under the District's specification entitled “PV POOL DECK RESURFACING PROJECT, SPEC NO. PVPD23-24” and to perform and complete in a good and workmanlike manner all the work pertaining thereto shown on the drawings and described in the specifications herein, to furnish at his or her own proper cost and expense all tools, equipment, labor, and materials necessary therefor, except such material and equipment as in said specifications as expressly stipulated to be furnished by said District, and to do everything required by this Agreement and the said specifications and drawings.

**ARTICLE II:** For furnishing all said materials and labor, furnishing and removing all plant, temporary works or structures, tools and equipment and doing all the work contemplated and embraced in this Agreement, also for all loss and damage arising out of the nature of the work aforesaid, or from the action of the elements, or from any unforeseen difficulties which may arise from or be encountered in the prosecution of the work until its acceptance by said District, and for all risks of every description connected with the work; also for all expenses incurred by or in consequence of the suspension or discontinuance of work, except such as in the said specifications are expressly stipulated to be borne by said District, and for well and faithfully completing the work the whole thereof, in the manner shown and described in said drawings and specifications and in accordance with the requirements of the Engineer, said District will pay and said Contractor shall receive in full compensation therefor the prices named in the Bidding Schedule of the Bid hereto attached.

**ARTICLE III:** All work to be done under this contract shall be completed **within FIFTEEN (15)** **consecutive working days**, exclusive of maintenance periods, beginning on the date stipulated in the written Notice to Proceed issued by the Engineer. Any changes in time and/or price are to be submitted to the District Engineer, in writing, within 3 days of the occurrence giving rise to the request and shall request a formal decision from the District within 3 days and shall include data supporting the request.

**ARTICLE IV:** The District hereby promises and agrees with said Contractor to employ, and does hereby employ, said Contractor to provide the materials and to do the work according to the terms and conditions herein contained and referred to for the price aforesaid, and hereby contracts to pay for the same, at the time, in the manner, and upon the conditions set forth in said specifications; and the said parties for themselves, their heirs, executors, administrators, successors, and assigns, do hereby agree to the full performance of the covenants herein contained.

**ARTICLE V:** The Notice Inviting Sealed Bids, the Instructions to Bidders, the Bid, the Specifications, and the Drawings mentioned therein, all addenda issued prior to the opening of the bid by the District, all contract change orders issued after execution of the Contract Agreement, the Special Provisions, Non-Collusion Declaration, Faithful Performance Bond, Payment Bond, all of which are essential parts of this contract, are hereby incorporated in and made part of this Agreement.

**ARTICLE VI:** Contractor acknowledges the provisions of Labor Code Section 1860 requiring every employer to be insured against liability for worker's compensation, or to undertake self-insurance in accordance with the provisions of that code, and certifies that it is in compliance with such provisions.

**ARTICLE VII:** The Contractor shall supply the District with Certificates evidencing all required insurance policies as described in the Instructions to Bidders.

**ARTICLE VIII:** The Contractor certifies that he or she is aware of the provisions of Public Contract Code Section 6109 and that any contractor or subcontractor who is ineligible under Labor Code Sections 17771.1 and 1777.7 is prohibited from working on this Project.

**ARTICLE IX:** Contractor acknowledges and agrees to comply with the provisions of the State Labor Code requiring every employer to pay at least the minimum prevailing rate of per diem wages for each craft, classification, or type of workman needed to execute this contract. State general prevailing wage determination as established by the California Department of Industrial Relations (available at <http://www.dir.ca.gov/DLSR/PWD/index.htm>) and the contractor shall post all required job site notices. The statutory provisions for penalties for failure to pay prevailing wages and/or failure to otherwise comply with state's wage and hour laws will be enforced. This contract is subject to compliance monitoring and enforcement by the Department of Industrial Relations. Contractor agrees that eight hours’ labor constitutes a legal day’s work.

The Contractor hereby agrees that the Contactor, and any subcontractor under the Contractor, shall pay not less than the general prevailing rate of per diem wages, as determined by the Director of the Department of Industrial Relations, to all workers employed in the execution of this contract as required under Subsection 5-3.2 of the 2021 Standard Specifications for Public Works Construction, and shall submit weekly to the District, certified copies of the payroll records for all said workers and shall comply with all statutory requirements relating to certified copies of payroll records, including the maintenance of the records, their certification, and their availability for inspection as required by Labor Code Section 1776 and as required under Subsection 5-3.3 of said Standard Specifications for Public Works Construction. In addition, the Contractor and any subcontractors must furnish electronic certified payroll records directly to the Labor Commissioner (aka Division of Labor Standards Enforcement) in a format prescribed by the Labor Commissioner no less than monthly. The Labor Commissioner may at any time require the contractors and subcontractors to furnish electronic certified payroll records.

The prevailing rate of per diem wages are on file at the Pleasant Valley Recreation & Park District, Department of Public Works, 1605 E. Burnley Street, Camarillo, CA 93010 , and are available to any interested party on request. The Contractor is required to post at the job site the prevailing rate of per diem wages as determined by the Director of the Department of Industrial Relations and other notices prescribed by regulation.

Contractor and any subcontractor under the Contractor must comply with the requirements of California Labor Code Sections 1777.5 and 1777.6 regarding the employment of apprentices.

**ARTICLE X:** The Contractor hereby agrees to indemnify and defend the District, its officers, agents, and employees against, and to hold and save them and each of them harmless from, any and all actions, suits, claims, damages to persons or property, losses, costs, penalties, obligations, errors, omissions, or liabilities (hereinafter “Claims or Liabilities”) that may be asserted or claimed by any person, firm, or entity arising out of or in connection with this Agreement, the construction of the project, any alleged breach or breach of any provision set forth in this Agreement or the plans or specifications for the project, design defects, any alleged violation or violation of any federal, state, or local, law, ordinance, statute, rule, regulation, or order, any failure or alleged failure to secure any applicable regulatory permit, license, or agreement, and the errors and omissions, willful misconduct, or negligence, whether said negligence is concurrent, active or passive, of the Contractor, its officers, agents, employees, or any other persons, except that the Contractor shall not be required to indemnify, defend, and hold harmless the District, its officers, agents, and employees against Claims or Liabilities caused by the negligence or willful misconduct or active negligence of the District, its officers, agents, or employees.

**ARTICLE XI:** The District, in accordance with Public Contract Code Section 22300, shall permit the substitution of securities for any moneys withheld by the District to secure performance under a contract. The District hereby incorporates herein all of the provisions set forth in Public Contract Code Section 22300.

**ARTICLE XII:** In the performance of this agreement, the Contractor shall not engage in, nor permit others he or she may hire to engage in, discrimination in the employment of persons because of their race, religious creed, color, or national origin, except as provided in Government Code Section 12940. Violation of this provision may result in the imposition of penalties as provided in Labor Code Section 1735.

**ARTICLE XIII:** Contractor will be compensated for any utility relocation required as part of the project which is not shown on the plans and Contractor will not be assessed liquidated damages for any delays caused by the District’s or a pubic utility’s failure to provide for removal or relocation of utility facilities.

**ARTICLE XIV:**  The Contractor shall maintain accounts and records, including personnel, property, and financial records, adequate to identify and account for all costs pertaining to the contract and such other records as may be deemed necessary by the District to assure proper accounting for all project funds, both federal and non-federal shares. These records will be made available for audit purposes to the District or any authorized representative and will be retained for 3 years after the expiration of this contract, unless permission to destroy them is granted by the District.

**ARTICLE XV:** No officer or employee of the District shall have any financial interest in this Agreement nor shall any such officer or employee participate in any decision relating to the Agreement which affects his or her financial interest or the financial interest of any corporation, partnership or association in which he or she is interested, in violation of any State statute or regulation. Similarly, Contractor warrants that it has not paid or given and will not pay or give any third party any money or other consideration for obtaining this Agreement.

**ARTICLE XVI:** The persons executing this Agreement on behalf of the parties hereto warrant that (i) such party is duly organized and existing, (ii) they are duly authorized to execute and deliver this Agreement on behalf of said party, (iii) by so executing this Agreement, such party is formally bound to the provisions of this Agreement, and (iv) the entering into this Agreement does not violate any provision of any other Agreement to which said party is bound.

**ARTICLE XVII:** Legal actions concerning any dispute, claim or matter arising out of or in relation to this Agreement shall be instituted in the Superior Court of the County of Ventura, State of California, or any other appropriate court in such county, and Contractor agrees to submit to the personal jurisdiction of such court in the event of such action.

**ARTICLE XVIII**: District will timely notify Contractor of any third party claim received by the District relating to this Agreement.

[Signatures on next page]

**DISTRICT: PLEASANT VALLEY RECREATION & PARK DISTRICT, CALIFORNIA**

Dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 202\_ By:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_, Chairman

ATTEST:

\_\_\_\_\_\_\_\_\_, Clerk of the Board

Dated \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 202\_

**CONTRACTOR: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

By:

AUTHORIZED REPRESENTATIVE

TITLE

By:

AUTHORIZED REPRESENTATIVE

TITLE

(Attach acknowledgment for each Authorized Representative of Contractor.)

Address:

Phone:

Fax:

Email:

**FAITHFUL PERFORMANCE BOND**

WHEREAS, the PLEASANT VALLEY RECREATION & PARK DISTRICT, (“District”), has awarded to \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, as Contractor (“Principal”), a Contract for the work entitled and described as follows **PV POOL DECK RESURFACING PROJECT, SPEC NO. PVPD23-24;**

WHEREAS, the Contractor is required under the terms of said Contract to furnish a bond for the faithful performance of the Contract;

NOW, THEREFORE, we the undersigned Contractor and Surety, are held and firmly bound unto the District in the sum of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ($\_\_\_\_\_\_\_\_\_\_\_\_\_\_), this amount being not less than one hundred percent (100%) of the total contract price, lawful money of the United States of America, for payment of which sum well and truly be made we bind ourselves, our heirs, executors, administrators, and successors, jointly and severally, firmly by these presents. In case suit is brought upon this bond, the Surety will pay a reasonable attorney’s fee to the District in an amount to be fixed by the court.

THE CONDITION OF THIS OBLIGATION IS SUCH THAT, if the hereby bound Contractor, or its heirs, executors, administrators, successors, or assigns, shall in all things stand and abide by, well and truly keep and perform all undertakings, terms, covenants, conditions, and agreements in the said Contract and any alteration thereof, made as therein provided, all within the time and in the manner designated and in all respects according to their true intent and meaning, then this obligation shall become null and void; otherwise it shall be and remain in full force and effect.

FURTHER, the said Surety, for value received, hereby stipulates and agrees that no change, extension of time, alteration, or modification of the Contract Documents or of the work to be performed thereunder shall in any way affect its obligations on this bond, and it does hereby waive notice of such change, extension of time, alteration, or modification of the Contract Documents or of the work to be performed thereunder.

**IN WITNESS WHEREOF,** we have hereunto set our hands and seals this \_\_ day of \_\_\_\_\_\_\_, 202\_\_.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ **PRINCIPAL** **SURETY**

Address of Surety:

CITY STATE ZIP

TELEPHONE

BY: BY:

(PRINCIPAL SEAL) (PRINCIPAL SEAL)

**LABOR AND MATERIAL BOND**

**(PAYMENT BOND)**

WHEREAS, the PLEASANT VALLEY RECREATION & PARK DISTRICT, (“District”), has awarded to \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, as Contractor (“Contractor”), a Contract for the work entitled and described as follows:

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

WHEREAS, said Contractor is required to furnish a bond in conjunction with said Contract, to secure the payment of claims of laborers, mechanics, material men, and other persons as provided by law;

NOW, THEREFORE, we the undersigned Contractor and Surety, are held and firmly bound unto the District in the sum of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ($\_\_\_\_\_\_\_\_\_\_\_\_\_\_), this amount being not less than one hundred percent (100%) of the total contract price, lawful money of the United States of America, for payment of which sum well and truly be made we bind ourselves, our heirs, executors, administrators, and successors, jointly and severally, firmly by these presents. In case suit is brought upon this bond, the Surety will pay a reasonable attorney’s fee to the District in an amount to be fixed by the court.

THE CONDITION OF THIS OBLIGATION IS SUCH THAT, if said Contractor, its heirs, executors, administrators, successors, assigns, or subcontractor fails to pay: (1) for any work, materials, services, provisions, provender, or other supplies, or for the use of implements of machinery, used in, upon, for, or about the performance of the work to be done, or for any work or labor thereon of any kind; (2) for work performed by any of the persons named in Civil Code Section 9100; (3) for any amounts due under the Unemployment Insurance Code with respect to work or labor performed under the contract; and/or (4) for any amounts required to be deducted, withheld, and paid over to the Employment Development Department from the wages of employees of the Contractor and/or its subcontractors pursuant to Section 13020 of the Unemployment Insurance Code with respect to such work and labor, then the Surety herein will pay for the same in an amount not exceeding the sum specified in this bond, otherwise the above obligation shall be void.

This bond shall inure to the benefit of any of the persons named in Civil Code Section 9100 so as to give a right of action to such persons or their assigns in any suit brought upon the bond. Moreover, if the District or any entity or person entitled to file stop payment notices is required to engage the services of an attorney in connection with the enforcement of this bond, each shall be liable for the reasonable attorney's fees incurred, with or without suit, in addition to the above sum.

Said Surety, for value received, hereby stipulates and agrees that no change, extension of time, alteration, or modification of the Contract Documents or of the work to be performed thereunder shall in any way affect its obligations on this bond, and it does hereby waive notice of such change, extension of time, alteration, or modification of the Contract Documents or of the work to be performed thereunder.

**IN WITNESS WHEREOF,** we have hereunto set our hands and seals this day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, 202\_\_.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ **CONTRACTOR** **SURETY**

ADDRESS OF SURETY

CITY STATE ZIP

TELEPHONE

BY: BY:

(CONTRACTOR SEAL) (CONTRACTOR SEAL)

**CONTRACTOR'S CERTIFICATE**

**REGARDING WORKERS’ COMPENSATION**

**Labor Code Section 3700**

"Every employer except the state shall secure the payment of compensation in one or more of the following ways:

(a) By being insured against liability to pay compensation by one or more insurers duly authorized to write compensation insurance in this state.

(b) By securing from the Director of Industrial Relations a certificate of consent to self-insure either as an individual employer, or as one employer in a group of employers, which may be given upon furnishing proof satisfactory to the Director of Industrial Relations of ability to self-insure and to pay any compensation that may become due to his or her employees.

 (c) For any county, city, city and county, municipal corporation, public district, public agency, or any political subdivision of the state, including each member of a pooling arrangement under a joint exercise of powers agreement (but not the state itself), by securing from the Director of Industrial Relations a certificate of consent to self-insure against workers' compensation claims, which certificate may be given upon furnishing proof satisfactory to the director of ability to administer workers' compensation claims properly, and to pay workers' compensation claims that may become due to its employees. On or before March 31, 1979, a political subdivision of the state which, on December 31, 1978, was uninsured for its liability to pay compensation, shall file a properly completed and executed application for a certificate of consent to self-insure against workers' compensation claims. The certificate shall be issued and be subject to the provisions of Section 3702.

For purposes of this section, "state" shall include the superior courts of California.”

I am aware of the provisions of Section 3700 of the Labor Code, which requires every employer to be insured against liability for workers’ compensation or to undertake self-insurance in accordance with the provisions of that code, and I will comply with such provisions before commencing the performance of the work of this contract.

**CONTRACTOR**

By:

AUTHORIZED REPRESENTATIVE

TITLE

(In accordance with Article 5 {commencing at Section 1860}, Chapter 1, Part 7, Division 2, of the Labor Code, the above certificate must be signed and filed with the awarding body prior to performing any work under this contract.)

**APPRENTICESHIP REQUIREMENTS**

**Labor Code, Division 2, Part 7, Chapter 1, Section 1773.3 “Notice; Required information”** states:

"(a)(1) An awarding agency shall provide notice to the Department of Industrial Relations of any public works contract subject to the requirements of this chapter, within five (5) days of the award.

(2) The notice shall be transmitted electronically in a format specified by the department and shall include the name of the contractor, any subcontractor listed on the successful bid, the bid and contract award dates, the contract amount, the estimated start and completion dates, job site location, and any additional information the department specifies that aids in the administration and enforcement of this chapter.

(b) In lieu of responding to any specific request for contract award information, the department may make the information provided by awarding bodies pursuant to this section available for public review on its Internet Web site.”

Also note **Labor Code Sections 1776(g), 1777.5 and 1777.7**.

**NOTICE**

**THE CONTRACTOR WILL BE REQUIRED TO FURNISH THE PLEASANT VALLEY RECREATION & PARK DISTRICT WITH THE CLASSIFICATIONS OF LABORERS TO BE USED FOR THE COMPLETION OF THIS PROJECT WITHIN THREE (3) WORKING DAYS AFTER NOTIFICATION OF AWARDING OF CONTRACT.**

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**GENERAL PROVISIONS**

**SCOPE OF WORK:** This project will take place within the Pleasant Valley Recreation & Park District. The work to be done consists of furnishing all materials, equipment, tools, labor, and incidentals as required by the Plans, Specifications, and Contract Documents. The general items of work are provided by Plans, Specifications and Contract Documents.

**LOCATION OF WORK:** The work will take place at 1030 Temple Avenue, in Camarillo, California.

**STANDARD SPECIFICATIONS:** The Standard Specifications of the District are contained in the 2021 Edition of the Standard Specifications for Public Works Construction, with amendments and supplements, as written and promulgated by the Joint Cooperative Committee of the Southern California Chapter of the American Public Works Association and the Southern California District of the Associated General Contractors of California (“Greenbook”). Copies of these Standard Specifications are available from the publisher, Building News, Incorporated, 990 Park Center Drive, Suite E, Vista, California 92081; telephone (760) 734-1113.

The Standard Specifications set forth above will control the General Provisions, Construction Materials, and Construction Methods for this Contract, except as amended by the Plans, Special Provisions, or other Contract Documents. The following Special Provisions are supplementary and in addition to the provisions of the Standard Specifications unless otherwise noted and the section numbers of the Special Provisions coincide with those of the said Standard Specifications. Only those sections requiring elaborations, amendments, specifying of the options, or additions are called out.

**LEGAL ADDRESS OF CONTRACTOR:** The address given in the Contractor's bid on which the contract is founded is hereby designated as the place to which all notices, letters, and other communications to the Contractor shall be mailed or delivered. Unless otherwise required by law, the mailing to or delivering at the above-named place of any notice, letter, or other communication by the District to the Contractor shall be deemed sufficient service thereof upon the Contractor. The date of said service shall be the date of such mailing or delivery. Such address may be changed at any time by a written notice signed by the Contractor and delivered to the Engineer.

**RECOVERY OF DAMAGES:** The making of an estimate and payment in accordance therewith shall not preclude the District from demanding and recovering from the Contractor such damages as it may sustain by reason of the Contractor’s failure to comply with the Specifications.

**MONIES MAY BE RETAINED:** The District may keep any monies which would otherwise be payable at any time hereunder and apply the same, or so much as may be necessary therefor, to the payment of any expenses, losses, or damages, as determined by the Engineer, incurred by the District, for which the Contractor is liable under the contract.

**SALES AND/OR TAXES:** Except as may be otherwise specifically provided herein, all sales and/or use taxes assessed by federal, state, or local authorities on materials used or furnished by the Contractor in performing the work hereunder shall be paid by the Contractor.

**ALLOWABLE VARIATION:** When in these Specifications a maximum or minimum, either in size, percentage, or thickness or relating to quality, character, or other matter, is allowed or prescribed, the work shall be accepted as in compliance if within such maximum or minimum so allowed thereby.

**PROTECTION OF PUBLIC UTILITIES:** The Contractor shall not be assessed liquidated damages for delay in completion of the project when such delay is caused by failure of the District or owner of a public utility to provide for removal or relocation of existing utility facilities. This Agreement is subject to Government Code Sections 4215 and 4126 – 4216.9. Contractor must notify utilities and obtain an identification number before excavation or be subject to liability for damages to subsurface installations.

**EMERGENCY INFORMATION:** The names, addresses, and telephone numbers of the Contractor and subcontractors, or their representatives, shall be filed with the Parks Department, the District Fire Department, and the County Sheriff's Department prior to beginning work.

**EMPLOYMENT OF APPRENTICES:** The Contractor's attention is directed to the provisions of Sections 1777.5 and 1777.6 of the Labor Code concerning the employment of apprentices by the Contractor or any Subcontractor under the Contractor. The Contractor, and any subcontractor under the Contractor, shall comply with the requirements of all statutory provisions relating to the employment of apprentices. Information relative to apprenticeship standards and administration of the apprenticeship program may be obtained from the Director of Industrial Relations, P.O. Box 603, San Francisco, California 94101 or from the Division of Apprenticeship Standards and its branch offices.

**PENALTIES FOR DISCRIMINATION IN EMPLOYMENT:** Any Contractor who shall be found in violation of the nondiscrimination provisions of the State of California Fair Employment Practices Act or similar provisions of federal law or executive order in the performance of any contract with the District shall be found in material breach of such contract and the District shall have power to cancel or suspend the Contractor, in whole or in part, or to deduct from the amount payable to such Contractor the sum of twenty-five dollars ($25.00) for each person for each calendar day during which such person was discriminated against, as damages for said breach of contract; or both. Only a finding of the State of California Fair Employment Practices Commission or the equivalent federal agency or officer shall constitute evidence of a violation of contract under this section.

The Contractor shall enclose with his or her bid a Compliance Report stating that he or she will pursue an affirmative course of action as required by the affirmative action guidelines.

**PROVISIONS REQUIRED BY LAW DEEMED INSERTED:** Each and every provision of law and clause required by law to be inserted in this contract shall be deemed to be inserted herein, and the contract shall be read and enforced as though it were included herein. If through mistake or otherwise any such provision is not inserted, or is not correctly inserted, then upon application of either party, the contract shall forthwith be physically amended to make such insertion or correction.

**PAYROLL RECORDS:** The Contractor's attention is directed to the following provisions of Labor Code Section 1776, “Payroll record of wages paid; Inspections; Forms; Effect of noncompliance; Penalties”. The Contractor shall be responsible for the compliance with these provisions by his or her subcontractors.

“(a) Each contractor and subcontractor shall keep an accurate payroll record, showing the name, address, social security number, work classification, straight time and overtime hours worked each day and week, and the actual per diem wages paid to each journeyman, apprentice, worker, or other employee employed by him or her in connection with the public work. Each payroll record shall contain or be verified by a written declaration that it is made under penalty of perjury, stating both of the following:

(1) The information contained in the payroll record is true and correct.

(2) The employer has complied with the requirements of Sections 1771, 1811, and 1815 for any work performed by his or her employees on the public works project.

(b) The payroll records enumerated under subdivision (a) shall be certified and shall be available for inspection at all reasonable hours at the principal office of the contractor on the following basis:

(1) A certified copy of an employee's payroll record shall be made available for inspection or furnished to the employee or his or her authorized representative on request.

(2) A certified copy of all payroll records enumerated in subdivision (a) shall be made available for inspection or furnished upon request to a representative of the body awarding the contract and the Division of Labor Standards Enforcement of the Department of Industrial Relations.

(3) A certified copy of all payroll records enumerated in subdivision (a) shall be made available upon request to the public for inspection or for copies thereof. However, a request by the public shall be made through either the body awarding the contract or the Division of Labor Standards Enforcement. If the requested payroll records have not been provided pursuant to paragraph (2), the requesting party shall, prior to being provided the records, reimburse the costs of preparation by the contractor, subcontractors, and the entity through which the request was made. The public may not be given access to such records at the principal office of the contractor.

(c) Unless required to be furnished directly to the Labor Commissioner in accordance with [paragraph (3) of subdivision (a) of Section 1771.4](https://a.next.westlaw.com/Link/Document/FullText?findType=L&pubNum=1000215&cite=CALBS1771.4&originatingDoc=N1D7F1F20025A11E49061EA59213A2019&refType=SP&originationContext=document&transitionType=DocumentItem&contextData=(sc.UserEnteredCitation)#co_pp_8b3b0000958a4), the certified payroll records shall be on forms provided by the Division of Labor Standards Enforcement or shall contain the same information as the forms provided by the division. The payroll records may consist of printouts of payroll data that are maintained as computer records, if printouts contain the same information as the forms provided by the division and the printouts are verified in the manner specified subdivision (a).

(d) A contractor or subcontractor shall file a certified copy of the records enumerated in subdivision (a) with the entity that requested the records within 10 days after receipt of a written request.

(e) Except as provided in subdivision (f), any copy of records made available for inspection as copies and furnished upon request to the public or any public agency by the awarding body or the Division of Labor Standards Enforcement shall be marked or obliterated to prevent disclosure of an individual's name, address, and social security number. The name and address of the contractor awarded the contract or the subcontractor performing the contract shall not be marked or obliterated. Any copy of records made available for inspection by, or furnished to, a multiemployer Taft-Hartley trust fund (29 U.S.C. Sec. 175a) shall be marked or obliterated only to prevent disclosure of an individual’s full social security number, but shall provide the last four digits of the social security number. Any copy of records made available for inspection by, or furnished to, a joint labor-management committee established pursuant to the federal Labor Management Cooperation Act of 1978 ([29 U.S.C. Sec. 175a](https://a.next.westlaw.com/Link/Document/FullText?findType=L&pubNum=1000546&cite=29USCAS175A&originatingDoc=N1D7F1F20025A11E49061EA59213A2019&refType=LQ&originationContext=document&transitionType=DocumentItem&contextData=(sc.UserEnteredCitation))) shall be marked or obliterated only to prevent disclosure of an individual's social security number.

(f)(1) Notwithstanding any other provision of law, agencies that are included in the Joint Enforcement Strike Force on the Underground Economy established pursuant to [Section 329 of the Unemployment Insurance Code](https://a.next.westlaw.com/Link/Document/FullText?findType=L&pubNum=1000224&cite=CAUIS329&originatingDoc=N1D7F1F20025A11E49061EA59213A2019&refType=LQ&originationContext=document&transitionType=DocumentItem&contextData=(sc.UserEnteredCitation)) and other law enforcement agencies investigating violations of law shall, upon request, be provided nonredacted copies of certified payroll records. Any copies of records or certified payroll made available for inspection and furnished upon request to the public by an agency included in the Joint Enforcement Strike Force on the Underground Economy or to a law enforcement agency investigating a violation of law shall be marked or redacted to prevent disclosure of an individual's name, address, and social security number.

(2) An employer shall not be liable for damages in a civil action for any reasonable act or omission taken in good faith in compliance with this subdivision.

(g) The contractor shall inform the body awarding the contract of the location of the records enumerated under subdivision (a), including the street address, city, and county, and shall, within five working days, provide a notice of a change of location and address.

(h) The contractor or subcontractor has 10 days in which to comply subsequent to receipt of written notice requesting the records enumerated in subdivision (a). In the event that the contractor or subcontractor fails to comply within the 10-day period, he or she shall, as a penalty to the state or political subdivision on whose behalf the contract is made or awarded, forfeit one hundred dollars ($100) for each calendar day, or portion thereof, for each worker, until strict compliance is effectuated. Upon the request of the Division of Labor Standards Enforcement, these penalties shall be withheld from progress payments then due. A contractor is not subject to a penalty assessment pursuant to this section due to the failure of a subcontractor to comply with this section.

(i) The body awarding the contract shall cause to be inserted in the contract stipulations to effectuate this section.

(j) The director shall adopt rules consistent with the California Public Records Act (Chapter 3.5 (commencing with Section 6250) of Division 7 of Title 1 of the Government Code) and the Information Practices Act of 1977 (Title 1.8 (commencing with Section 1798) of Part 4 of Division 3 of the Civil Code) governing the release of these records, including the establishment of reasonable fees to be charged for reproducing copies of records required by this section.

**ASSIGNMENT OF ANTITRUST ACTIONS:** The Contractor's attention is directed to the following provision of the Public Contracts Code, Section 7103.5, which shall be applicable to the Contractor and his or her subcontractors:

"(b) In entering into a public works contract or a subcontract to supply goods, services, or materials pursuant to a public works contract, the contractor or subcontractor offers and agrees to assign to the awarding body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 (commencing with Section 16700) of Part 2 Division 7 of Business and Professions Code), arising from purchases of goods, services, or materials pursuant to the public works contract or the subcontract. This assignment shall be made and become effective at the time the awarding body tenders final payment to the contractor, without further acknowledgment by the parties.”

**CONSTRUCTION SCHEDULES:** Prior to issuing the “Notice to Proceed”, the Engineer will schedule a preconstruction meeting with the Contractor to review the proposed construction schedule and delivery dates, arrange utility coordination, discuss construction methods, and clarify inspection procedures. The Contractor must provide to the Engineer, at the time of the pre-construction meeting, a schedule in the form of a Gantt Chart for review and approval. Any change in the construction schedule will require the Contractor to provide revised charts of those changes to the Engineer within two (2) working days. The "Notice to Proceed” will be issued upon approval of the project schedule. Requests for changes in the schedule shall be submitted by the Contractor to the Engineer in writing for approval at least 48 hours prior to the scheduled operations on the streets affected.

The schedule shall be broken down into activities by street with durations no greater than one week. No more than 15% of the activities may be on the critical path of the baseline schedule. The Engineer will review the baseline schedule and the Contractor will make any reasonable changes requested to make the schedule acceptable.

If at any time project completion is ten or more working days behind schedule, the Contractor shall submit a recovery schedule, subject to approval, showing how the original completion date will be met.

**CONSTRUCTION WORKING HOURS:** The Contractor's regular hours of work will be from 7:00 AM to 5:00 PM on all working days as defined in Section 1-2 of the Greennbook .

**EQUIVALENT MATERIALS:** Approval of equipment and materials offered as equivalents to those specified must be obtained in writing from the District prior to the opening of bids. Requests for consideration of equivalents must be submitted in writing allowing five (5) working days for complete consideration of all specifications, samples, references, tests, and other details to the full satisfaction of the District.

**SPECIAL PROVISIONS**

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24\_\_\_\_\_**

**FISCAL YEAR 2023-2024**

**1. GENERAL**

**A. THE REQUIREMENT:** All work embraced herein shall be accomplished in accordance with the applicable portions of the "Standard Specifications for Public Works Construction" 2021 edition, plus any supplements, published, herein referred to as "Standard Specifications," except as modified by the General Conditions, these Special Provisions, Standard Drawings and the Project Plans (“Greenbook”). In addition to the above, the Contractor shall comply with the requirements of the following:

(1) Notice Inviting Sealed Bids

(2) Instructions to Bidders

(3) Bid

(4) Bid Bond

(5) Information Required of Bidder

(6) Agreement

(7) Faithful Performance Bond

(8) Payment Bond (Labor and Material Bond)

**B. DEFINITION OF TERMS:** Wherever in the Standard Specifications terms are used, they shall be understood to mean and refer to the following:

(1) District – The Pleasant Valley Recreation & Park District

(2) Board - The District’s governing board

(3) Director, Engineer - The District’s Public Works and District Engineer, acting either directly or through authorized agents. Also referred to herein as District Engineer.

(4) Other terms appearing in the Standard Specifications, the General Conditions, and these Special Provisions shall have the intent and meaning specified in Section 1 of the Standard Specifications.

**C. SCOPE AND CONTROL OF THE WORK:**

PROJECT PLANS: The location of the work, its general nature, extent, form and detail of the various features are shown on drawings accompanying and made a part of these specifications.

Section 2 is amended by adding thereto the following new Subsection 2-1.1 Plans and Specifications:

“2-1.1 Plans and Specifications. The Contractor shall maintain a control set of Plans and Specifications on the project site at all times. All final locations determined in the field, and any deviations from the Plans and Specifications, shall be marked in red on this control set to show the as-built conditions. Upon completion of all work, the Contractor shall return the control set to the Engineer. Final payment will not be made until this requirement is met.”

Section 2 is amended by adding thereto the following new Subsection 2-1.2 Record Drawings:

“2-1.2 Record Drawings.

All corrections on record drawings shall be done in red ink. Record drawings shall be a control set of the construction plans kept on the site for daily recording of “as built” conditions. Show dimensioned locations of all buried facilities, such as drains, sumps, pipe, valves, electrical conduits, and irrigation wires.

Dimensions must be taken from above ground permanent architectural objects, not plants or irrigation heads. All dimensions, notes, etc., shall be legible.

Record drawings shall be reviewed prior to all progress payment requests, and submitted prior to final inspection.”

**D. COMPLETION OF WORK:**

(1) All work to be done under this contract shall be completed **within FIFTEEN (15) consecutive working days,** exclusive of maintenance periods, beginning on the date stipulated in the written "Notice to Proceed" issued by the Engineer.

(2) In the event that the Engineer is of the opinion that the work is being inadequately or improperly prosecuted in any respect, he or she may demand that the Contractor improve or change the prosecution of the work in such manner as to assure proper and timely completion.

**E. FINAL INVOICE AND PAYMENT:**

(1) Whenever in the opinion of the Engineer the Contractor shall have completely performed the contract on his or her part, the Engineer shall notify the District that the contract has been completed in its entirety. He or she shall request that the District accept the work and that the District of the Board be authorized to file, on behalf of the District, in the office of the Ventura County Recorder, a notice of completion of the work herein agreed to be done by the Contractor. The Contractor will then submit to the Engineer for approval a written statement of the final quantities of contract items for inclusion in the final invoice. Upon receipt of such statement, the Engineer shall check the quantities included therein and shall authorize the Contractor to submit an invoice which in the Engineer's opinion shall be just and fair, covering the amount and value of the total amount of work done by the Contractor, not including the work that has already been invoiced by the Contractor. District will pay this invoice less any amounts District is required to withhold as described elsewhere in the Contract Documents.

(2) On the expiration of sixty (60) calendar days after recordation of the acceptance of the project by Ventura County Recorder, the District shall pay to the Contractor the amount remaining after deducting from the amount or value stated in the invoice all prior payments to the Contractor and all amounts to be kept and retained under the provisions of the contract and 150% of all disputed amounts, and shall release the faithful performance bond and the labor and material bond once all applicable disputes have been resolved. The District will comply with Public Contract Code Section 7107 and other applicable law regarding the release of retention.

**F. RETENTION:** The District will deduct a five percent (5%) retention from all progress payments as specified in Section 7-3.2 of the 2021 Standard Specifications for Public Works Construction.

**G. SUBSTITUTION OF SECURITIES FOR RETENTION:** Public Contract Code Section 22300 is hereby incorporated by reference. The substitution of securities for any moneys withheld by a public agency to ensure performance under a contract shall be permitted by the District.

**H. NO PERSONAL LIABILITY:** No agent of the Pleasant Valley Recreation & Park District shall be personally responsible for any liability arising under the contract. No claim shall be made or filed, and neither the District nor any of its agents shall be liable for, or held to pay money, except as specifically provided in the contract.

**I. UNPAID CLAIMS:** If, upon or before the completion of the work herein agreed to be performed or at any time prior to the expiration of the period within which claims of lien may be filed for record as prescribed by Civil Code Section 8416, any person or persons claiming to have performed any labor or furnished any material, supplies, or services toward the performance or completion of this contract or that they have agreed to do so, shall file with the District a verified statement of such claim, stating in general terms the kind of labor and materials and the name of the person to or for whom the same was done or furnished, or both, and the amount in value, as near as may be, of that already done or furnished, or both, together with a statement that the same has not been paid, or if any person or persons shall bring against the District or against any agent or agents thereof any action to enforce such claim, the District shall until the discharge thereof withhold from the moneys under its control so much of said moneys due or to become due the Contractor under this contract as shall be sufficient to satisfy and discharge the amount in such notice or under such action claimed to be due, together with the costs thereof; provided, that if the District shall in its discretion permit the Contractor to file such additional bond as is authorized by Civil Code Section 9364 in a sum equal to 125% of the amount of the claim, said moneys shall not thereafter be withheld on account of such claim.

**J. ADDITIONAL SURETY:** If during the continuance of the contract any of the sureties upon the faithful performance bond in the opinion of the Engineer are or become insufficient, he or she may require additional sufficient sureties which the Contractor shall furnish to the satisfaction of the Engineer within fifteen (15) days after notice and, in default thereof, the contract may be suspended and the work completed as provided in Section 6 of the Standard Specifications.

**K. NOISE CONTROL REQUIREMENTS:** The Contractor shall comply with all local sound control and noise level rules, regulations, and ordinances that apply to any work performed pursuant to the contract.

Each internal combustion engine, used for any purpose on the job or related to the job, shall be equipped with a muffler of a type recommended by the manufacturer. No internal combustion engine shall be operated on the project without said muffler. The noise level from the Contractor's operations, between the hours of 7:00 A.M. and 5:00 P.M., shall not exceed 86 dBA at a distance of fifty (50) feet. This requirement in no way relieves the Contractor from responsibility for complying with the District Code Chapter 8.20 "Noise Control" regulating noise level. Said noise level requirements shall apply to all equipment on the job or related to the job, including but not limited to trucks, transmit mixers, or transient equipment that may or may not be owned by the Contractor. The use of loud sound signals shall be avoided in favor of light warnings except those required by safety laws for the protection of personnel.

Full compensation for conforming to the requirements of this section shall be considered as included in the unit cost for the various contract items of work involved, and no additional compensation will be allowed therefor.

**L. PERMITS AND LICENSES:** The Contractor shall procure all permits and licenses, pay all charges and fees, and give all notices necessary and incident to the due and lawful prosecution of the work. The Contractor shall also ensure that all subcontractors obtain required permits and licenses.

The Environmental Quality Act of 1970 (Chapter 1433, Stats. 1970), as amended by Chapter 1154, Stats. 1972, may be applicable to permits, licenses, and other authorizations which the Contractor must obtain from local agencies in connection with performing the work of the contract. The Contractor shall comply with all applicable environmental laws and regulations and conditions on the project in obtaining such permits, licenses, and other authorizations, and they shall be obtained in sufficient time to prevent delays to the work, and in undertaking the construction of the project. Contractor shall also comply with all applicable mandatory standards and policies relating to energy efficiency.

In the event that the District has obtained permits, licenses, or other authorizations applicable to the work in conformance with the requirements in said Environmental Quality Act of 1970, the Contractor shall comply with the provisions of said permits, licenses, and other authorizations.

**M. PAYMENTS:** Attention is directed to Subsection 7-3.2 of the Standard Specifications for partial payment and final payment requirements. No partial payment will be made for any materials on hand which are furnished but not incorporated in the work.

**N. LEGAL ACTIONS AGAINST THE DISTRICT:** In the event litigation is brought against the District concerning compliance by the District with State or Federal laws, rules, or regulations applicable to highway work, the provisions of this section shall apply.

(1) If, pursuant to court order, the District prohibits the Contractor from performing all or any portion of the work, the delay will be considered a utility delay within the meaning of Subsection 4-2.5 of the Standard Specifications unless the contract is terminated as hereinafter provided, in which event compensation payable to the Contractor shall be determined in accordance with said termination provisions.

(2) If, pursuant to court order (other than an order to show cause) the District is prohibited from requiring the Contractor to perform all or any portion of the work, the District may, if it so elects, eliminate the enjoined work pursuant to Section 2-7 of the Standard Specifications or terminate the contact in accordance with Subsections 6-6 and 6-7 of the Standard Specifications.

(3) If the final judgment in the action prohibits the District from requiring the Contractor to perform all or any portion of the work, the District will either eliminate the enjoined work pursuant to Section 2-7 of the Standard Specifications or terminate the contract in accordance with Subsections 6-6 and 6-7 of the Standard Specifications.

(4) Termination of the contract and the total compensation payable to the Contractor in the event of termination shall be governed by the following:

(a) The Engineer will issue the Contractor a written notice specifying that the contract is to be terminated. Upon receipt of said written notice and, except as otherwise directed in writing by the Engineer, the Contractor shall:

[1] Stop all work under the contract, except that portion of the work specifically directed to be completed prior to acceptance.

[2] Perform work the Engineer deems necessary to secure the project for termination.

[3] Remove equipment and plan from the site of the work.

[4] Take such action as is necessary to protect materials from damage.

[5] Notify all Subcontractors and suppliers that the contract is being terminated and that their contracts of orders are not to be further performed unless otherwise authorized in writing by the Engineer.

[6] Provide the Engineer with an inventory list of all materials previously produced, purchased, or ordered from suppliers for use in the work and not yet used in the work, including its storage location and such other information as the Engineer may request.

[7] Dispose of materials not yet used in the work as directed by Engineer. It shall be the Contractor's responsibility to provide the District with good title to all materials purchased by the District hereunder, including materials for which partial payment has been made as provided in Subsection 7-3.2 of the Standard Specifications, and with bills of sale or other documents of title for such materials.

[8] Subject to the prior written approval of the Engineer, settle all outstanding liabilities and all claims arising out of subcontracts or orders for materials terminated hereunder. To the extent directed by the Engineer, the Contractor shall assign to the District all the right, title, and interest of the Contractor under subcontracts or orders for materials terminated hereunder.

[9] Furnish the Engineer with the documentation required to be furnished by the Contractor under the provisions of the contract including, on projects as to which Federal funds are involved, all documentation required under the Federal requirements included in the contract.

[10] Take such other actions as the Engineer may direct.

(b) Acceptance of the contract as hereinafter specified shall not relieve the Contractor of responsibility for damage to materials except as follows:

[1] The Contractor's responsibility for damage to materials for which partial payment has been made as provided in Subsection 7-3.2 of the Standard Specifications, and for materials furnished by the District for use in the work and unused, shall terminate when the Engineer certifies that such materials have been stored in the manner and at the locations he or she has directed.

[2] The Contractor's responsibility for damage to materials purchased by the District subsequent to the issuance of the notice that the contract is to be terminated shall terminate when title and delivery of the materials has been taken by the District.

[3] When the Engineer determines that the Contractor has completed the work under the contract directed to be completed prior to termination and such other work as may have been ordered to secure the project for termination, he or she will recommend that the Engineer formally accept the contract, and immediately upon and after such acceptance by the Engineer, the Contractor will not be required to perform any further work thereon and shall be relieved of his or her contractual responsibilities for injury to persons or property which occurs after the formal acceptance of the project by the Engineer.

(c) The total compensation to be paid to the Contractor shall be determined by the Engineer on the basis of the following:

[1] The reasonable cost to the Contractor, without profit, for all work performed under the contract, including mobilization, demobilization, and work done to secure the project for termination. Reasonable cost will include a reasonable allowance for project overhead and general administrative overhead not to exceed a total of seven percent (7%) of direct costs of such work.

When in the opinion of the Engineer, the cost of a contract item of work is excessively high due to costs incurred to remedy or replace defective or rejected work, the reasonable cost to be allowed will be the estimated reasonable cost of performing such work in compliance with the requirements of the plans and specifications and the excessive actual cost shall be disallowed.

[2] A reasonable allowance for profit on the cost of the work performed as determined under Subsection (a), provided the Contractor establishes to the satisfaction of the Engineer that it is reasonably probable that he or she would have made a profit had the contract been completed and provided further that the profit allowed shall in no event exceed four percent (4%) of said cost.

[3] The reasonable cost to the Contractor of handling material returned to the vendor, delivered to the District, or otherwise disposed of as directed by the Engineer.

[4] A reasonable allowance for the Contractor's administrative costs in determining the amount payable due to termination of the contract.

All records of the Contractor and his or her subcontractors, necessary to determine compensation in accordance with the provisions of this section, shall be open to inspection or audit by representatives of the District at all times after issuance of the notice that the contract is to be terminated and for a period of three years, and such records shall be retained for that period.

After acceptance of the work by the Engineer, the Engineer may make payments on the basis of interim estimates pending issuance of the Final Estimate when in his or her opinion the amount thus paid, together with all amounts previously paid, will not result in total compensation in excess of that to which the Contractor will be entitled. All payments, including payment upon the Final Estimate, shall be subject to deduction for prior payments and amounts, if any, to be kept or retained under the provisions of the contract.

The provisions of this section shall be included in all subcontracts.

**O. TRENCHING:** In accordance with Section 6705 of the California Labor Code,

No contract for public works involving an estimated expenditure in excess of twenty-five thousand dollars ($25,000), for the excavation of any trench or trenches five feet or more in depth, shall be awarded unless it contains a clause requiring submission by the Contractor and acceptance by the awarding body or by a registered civil or structural engineer employed by the awarding body, to whom authority to accept has been delegated, in advance of excavation, of a detailed plan showing the design of shoring, bracing, sloping, or other provisions to be made for worker protection from the hazard of caving ground during the excavation of such trench or trenches. If such plan varies from the shoring system standards, the plan shall be prepared by a registered civil or structural engineer.

Nothing in this section shall be deemed to allow the use of a shoring, sloping, or protective system less effective than that required by the Construction Safety Orders.

Nothing in this section shall be construed to impose tort liability on the awarding body or any of its employees.

The terms "public works" and "awarding body," as used in this section, shall have the same meaning as in Sections 1720 and 1722, respectively, of the Labor Code.”

In addition, pursuant to Public Contracts Code § 7104, if the project involves digging trenches or other excavations that extend deeper than four feet below the surface:

(a) That the contractor shall promptly, and before the following conditions are disturbed, notify the local public entity, in writing, of any:

(1) Material that the contractor believes may be material that is hazardous waste, as defined in Section 25117 of the Health and Safety Code, that is required to be removed to a Class I, Class II, or Class III disposal site in accordance with provisions of existing law.

(2) Subsurface or latent physical conditions at the site differing from those indicated by information about the site made available to bidders prior to the deadline for submitting bids.

(3) Unknown physical conditions at the site of any unusual nature, different materially from those ordinarily encountered and generally recognized as inherent in work of the character provided for in the contract.

(b) That the local public entity shall promptly investigate the conditions, and if it finds that the conditions do materially so differ, or do involve hazardous waste, and cause a decrease or increase in the contractor’s cost of, or the time required for, performance of any part of the work shall issue a change order under the procedures described in the contract.

(c) That, in the event that a dispute arises between the local public entity and the contractor whether the conditions materially differ, or involve hazardous waste, or cause a decrease or increase in the contractor’s cost of, or time required for, performance of any part of the work, the contractor shall not be excused from any scheduled completion date provided for by the contract, but shall proceed with all work to be performed under the contract. The contractor shall retain any and all rights provided either by contract or by law which pertain to the resolution of disputes and protests between the contracting parties.”

Full compensation for sheeting, shoring, bracing, sloping, and all other provisions required for worker protection shall be considered as included in the contract price shown in the appropriate Bid Item, and no additional compensation will be allowed therefor.

**P. CHANGES IN WORK:**

The following Section is hereby added:

“7.4.3.3 Mark-up Cap. Work by the Subcontractor the Contractor’s total mark-up is not to exceed 12%.”

**Q. CONTROL OF MATERIALS:**

The following sections are added to Section 4:

“4-1.1 General. The Contractor and all subcontractors, suppliers, and vendors shall guarantee that all work performed under this contract fully meets the requirements thereof as to quality of workmanship. Should any defects become evident within a period of one year from the date of the acceptance of the work by the District’s Board, the Contractor shall, at his or her own expense, make any repair or replacement necessary to restore the work to full compliance with these Special Provisions.

Such repair and replacement shall be made promptly upon receipt of written notice from the Engineer. If the Contractor fails to make such repair and replacement promptly, the Engineer may cause the work to be done and the costs incurred thereby shall become the liability of the Contractor and his or her Surety.

If, in the opinion of the Engineer, defective work creates a dangerous condition or requires immediate correction or attention to prevent further loss by the District or to prevent interruption of operations of the District, the District will attempt to give the notice required by this article. If the Contractor cannot be contacted or does not comply with the Engineer's request for correction within a reasonable time as determined by the Engineer, the District may, notwithstanding the provisions of this article, proceed to make such correction or attention and the costs of such correction or attention shall be charged against the Contractor.

The foregoing obligation shall be secured by the surety bond in a form approved by the Engineer in an amount not less than ten (10%) of the final contract price or $1,000.00, whichever is greater, and shall be delivered to the Engineer prior to final acceptance of the work. Payment for fulfilling the requirements of this section shall be considered as included in the unit cost for the various contract items of work, and no additional compensation will be allowed therefor.”

“4-4.1 Test of Materials. Except as elsewhere specified, the District will bear the cost of testing material and/or workmanship that meets or exceeds the requirements indicated in the project specifications contained herein, Standard Specifications and the Special Provisions. The cost of all other tests, including the retesting of material or workmanship that fails to pass the first test, shall be borne by the Contractor.”

Section 4-5 shall be replaced with the following:

“4-5 Certification. A Certificate of Compliance shall be furnished prior to the use of any materials for which these specifications or the special provisions require that such a certificate be furnished. In addition, when so authorized in these specifications or in the Special Provisions, the Engineer may permit the use of certain materials or assemblies prior to sampling and testing if accompanied by a Certificate of Compliance. The certificate shall be signed by the manufacturer of the material or the manufacturer of assembled materials and shall state that the materials involved comply in all respects with the requirements of the specifications. A Certificate of Compliance shall be furnished with each lot of material delivered to the work and the lot so certified shall be clearly identified in the certificate.”

**R. CARB Compliance**. For a project involving the use of in-use off-road diesel-fueled vehicles, as defined by 13 CCR 2449, Contractor shall obtain copies of the valid Certificates of Reported Compliance, as described in 13 CCR 2449(n), for the fleet performing services pursuant to this contract and all listed subcontractors, if applicable, prior to commencing any work pursuant to this Contract or any renewed contract with that fleet. Contractor shall indemnify, defend and hold harmless the District, its officers, agents, employees and directors from any liability imposed arising from Contractor’s violation of any regulation set forth in 13 CCR 2449.

**S. CONFERENCES AND MEETING:** When and as directed by the Engineer, the Contractor shall attend all conferences and meetings that the Engineer deems necessary for the proper progress of work under this contract.

**T. UNDERGROUND SERVICE ALERT:** Except in an emergency, the Contractor, prior to conducting any excavation or resurfacing, shall contact the appropriate regional notification center, at least two working days prior to commencing that excavation or resurfacing. The regional notification center shall provide an inquiry center and shall notify any member, if known, who has a subsurface installation in the area of the proposed excavation or resurfacing.

Underground Service Alert may be contacted by calling 1-800-422-4133.

**U. RESOLUTION OF ALL CONSTRUCTION CLAIMS:**

### **“9204. Legislative findings and declarations regarding timely and complete payment of contractors for public works projects; claims process**

(a) The Legislature finds and declares that it is in the best interests of the state and its citizens to ensure that all construction business performed on a public works project in the state that is complete and not in dispute is paid in full and in a timely manner.

(b) Notwithstanding any other law, including, but not limited to, Article 7.1 (commencing with Section 10240) of Chapter 1 of Part 2, Chapter 10 (commencing with Section 19100) of Part 2, and Article 1.5 (commencing with Section 20104) of Chapter 1 of Part 3, this section shall apply to any claim by a contractor in connection with a public works project.

(c) For purposes of this section:

(1) “Claim” means a separate demand by a contractor sent by registered mail or certified mail with return receipt requested, for one or more of the following:

(A) A time extension, including, without limitation, for relief from damages or penalties for delay assessed by a public entity under a contract for a public works project.

(B) Payment by the public entity of money or damages arising from work done by, or on behalf of, the contractor pursuant to the contract for a public works project and payment for which is not otherwise expressly provided or to which the claimant is not otherwise entitled.

(C) Payment of an amount that is disputed by the public entity.

(2) “Contractor” means any type of contractor within the meaning of Chapter 9 (commencing with Section 7000) of Division 3 of the Business and Professions Code who has entered into a direct contract with a public entity for a public works project.

(3)(A) “Public entity” means, without limitation, except as provided in subparagraph (B), a state agency, department, office, division, bureau, board, or commission, the California State University, the University of California, a city, including a charter city, county, including a charter county, city and county, including a charter city and county, district, special district, public authority, political subdivision, public corporation, or nonprofit transit corporation wholly owned by a public agency and formed to carry out the purposes of the public agency.

(B) “Public entity” shall not include the following:

(i) The Department of Water Resources as to any project under the jurisdiction of that department.

(ii) The Department of Transportation as to any project under the jurisdiction of that department.

(iii) The Department of Parks and Recreation as to any project under the jurisdiction of that department.

(iv) The Department of Corrections and Rehabilitation with respect to any project under its jurisdiction pursuant to Chapter 11 (commencing with Section 7000) of Title 7 of Part 3 of the Penal Code.

(v) The Military Department as to any project under the jurisdiction of that department.

(vi) The Department of General Services as to all other projects.

(vii) The High-Speed Rail Authority.

(4) “Public works project” means the erection, construction, alteration, repair, or improvement of any public structure, building, road, or other public improvement of any kind.

(5) “Subcontractor” means any type of contractor within the meaning of Chapter 9 (commencing with Section 7000) of Division 3 of the Business and Professions Code who either is in direct contract with a contractor or is a lower tier subcontractor.

(d)(1)(A) Upon receipt of a claim pursuant to this section, the public entity to which the claim applies shall conduct a reasonable review of the claim and, within a period not to exceed 45 days, shall provide the claimant a written statement identifying what portion of the claim is disputed and what portion is undisputed. Upon receipt of a claim, a public entity and a contractor may, by mutual agreement, extend the time period provided in this subdivision.

(B) The claimant shall furnish reasonable documentation to support the claim.

(C) If the public entity needs approval from its governing body to provide the claimant a written statement identifying the disputed portion and the undisputed portion of the claim, and the governing body does not meet within the 45 days or within the mutually agreed to extension of time following receipt of a claim sent by registered mail or certified mail, return receipt requested, the public entity shall have up to three days following the next duly publicly noticed meeting of the governing body after the 45-day period, or extension, expires to provide the claimant a written statement identifying the disputed portion and the undisputed portion.

(D) Any payment due on an undisputed portion of the claim shall be processed and made within 60 days after the public entity issues its written statement. If the public entity fails to issue a written statement, paragraph (3) shall apply.

(2)(A) If the claimant disputes the public entity's written response, or if the public entity fails to respond to a claim issued pursuant to this section within the time prescribed, the claimant may demand in writing an informal conference to meet and confer for settlement of the issues in dispute. Upon receipt of a demand in writing sent by registered mail or certified mail, return receipt requested, the public entity shall schedule a meet and confer conference within 30 days for settlement of the dispute.

(B) Within 10 business days following the conclusion of the meet and confer conference, if the claim or any portion of the claim remains in dispute, the public entity shall provide the claimant a written statement identifying the portion of the claim that remains in dispute and the portion that is undisputed. Any payment due on an undisputed portion of the claim shall be processed and made within 60 days after the public entity issues its written statement. Any disputed portion of the claim, as identified by the contractor in writing, shall be submitted to nonbinding mediation, with the public entity and the claimant sharing the associated costs equally. The public entity and claimant shall mutually agree to a mediator within 10 business days after the disputed portion of the claim has been identified in writing. If the parties cannot agree upon a mediator, each party shall select a mediator and those mediators shall select a qualified neutral third party to mediate with regard to the disputed portion of the claim. Each party shall bear the fees and costs charged by its respective mediator in connection with the selection of the neutral mediator. If mediation is unsuccessful, the parts of the claim remaining in dispute shall be subject to applicable procedures outside this section.

(C) For purposes of this section, mediation includes any nonbinding process, including, but not limited to, neutral evaluation or a dispute review board, in which an independent third party or board assists the parties in dispute resolution through negotiation or by issuance of an evaluation. Any mediation utilized shall conform to the timeframes in this section.

(D) Unless otherwise agreed to by the public entity and the contractor in writing, the mediation conducted pursuant to this section shall excuse any further obligation under Section 20104.4 to mediate after litigation has been commenced.

(E) This section does not preclude a public entity from requiring arbitration of disputes under private arbitration or the Public Works Contract Arbitration Program, if mediation under this section does not resolve the parties' dispute.

(3) Failure by the public entity to respond to a claim from a contractor within the time periods described in this subdivision or to otherwise meet the time requirements of this section shall result in the claim being deemed rejected in its entirety. A claim that is denied by reason of the public entity's failure to have responded to a claim, or its failure to otherwise meet the time requirements of this section, shall not constitute an adverse finding with regard to the merits of the claim or the responsibility or qualifications of the claimant.

(4) Amounts not paid in a timely manner as required by this section shall bear interest at 7 percent per annum.

(5) If a subcontractor or a lower tier subcontractor lacks legal standing to assert a claim against a public entity because privity of contract does not exist, the contractor may present to the public entity a claim on behalf of a subcontractor or lower tier subcontractor. A subcontractor may request in writing, either on their own behalf or on behalf of a lower tier subcontractor, that the contractor present a claim for work which was performed by the subcontractor or by a lower tier subcontractor on behalf of the subcontractor. The subcontractor requesting that the claim be presented to the public entity shall furnish reasonable documentation to support the claim. Within 45 days of receipt of this written request, the contractor shall notify the subcontractor in writing as to whether the contractor presented the claim to the public entity and, if the original contractor did not present the claim, provide the subcontractor with a statement of the reasons for not having done so.

(e) The text of this section or a summary of it shall be set forth in the plans or specifications for any public works project that may give rise to a claim under this section.

(f) A waiver of the rights granted by this section is void and contrary to public policy, provided, however, that (1) upon receipt of a claim, the parties may mutually agree to waive, in writing, mediation and proceed directly to the commencement of a civil action or binding arbitration, as applicable; and (2) a public entity may prescribe reasonable change order, claim, and dispute resolution procedures and requirements in addition to the provisions of this section, so long as the contractual provisions do not conflict with or otherwise impair the timeframes and procedures set forth in this section.

(g) This section applies to contracts entered into on or after January 1, 2017.

(h) Nothing in this section shall impose liability upon a public entity that makes loans or grants available through a competitive application process, for the failure of an awardee to meet its contractual obligations.

(i) This section shall remain in effect only until January 1, 2027, and as of that date is repealed, unless a later enacted statute that is enacted before January 1, 2027, deletes or extends that date.”

**RESOLUTION OF CONSTRUCTION CLAIMS OF $375,000 OR LESS:**

“**20104. Application of article; provisions included in plans and specifications**

(a) (1) This article applies to all public works claims of three hundred seventy-five thousand dollars ($375,000) or less which arise between contractor and a local agency.

(2) This article shall not apply to any claims resulting from a contract between a contractor and a public agency when the public agency has elected to resolve any disputes pursuant to Article 7.1 (commencing with Section 10240) of Chapter 1 of Part 2.

(b) (1) "Public work" means “public works contract” as defined in Section 1101 but does not include any work or improvement contracted for by the State or the Regents of the University of California.

(2) "Claim" means a separate demand by the contractor for (A) a time extension, (B) payment of money or damages arising from work done by or on behalf of, the contractor pursuant to the contract for a public work and payment of which is not otherwise expressly provided for or the claimant is not otherwise entitled to, or (C) an amount the payment of which disputed by the local agency.

(c) The provisions of this article or a summary thereof shall be set forth in the plans or specifications for any work which may give rise to a claim under this article.

(d) This article applies only to contracts entered into on or after January 1, 1991.”

“**20104.2. Claims; requirements; tort claims excluded**

For any claim subject to this article, the following requirements apply:

(a) The claim shall be in writing and include the documents necessary to substantiate the claim. Claims must be filed on or before the date of final payment. Nothing in this subdivision is intended to extend the time limit or supersede notice requirements otherwise provided by contract for the filing of claims.

(b) (1) For claims of less than fifty thousand dollars ($50,000), the local agency shall respond in writing to any written claim within 45 days of receipt of the claim, or may request, in writing, within 30 days of receipt of the claim, any additional documentation supporting the claim or relating to defenses to the claim the local agency may have against the claimant.

(2) If additional information is thereafter required, it shall be requested and provided pursuant to this subdivision, upon mutual agreement of the local agency and the claimant.

(3) The local agency's written response to the claim, as further documented, shall be submitted to the claimant within 15 days after receipt of the further documentation or within a period of time no greater than that taken by the claimant in producing the additional information, whichever is greater.

(c) (1) For claims of over fifty thousand dollars ($50,000) and less than or equal to three hundred seventy-five thousand dollars ($375,000), the local agency shall respond in writing to all written claims within 60 days of receipt of the claim, or may request, in writing, within 30 days of receipt of the claim, any additional documentation supporting the claim or relating to defenses to the claim the local agency may have against the claimant.

(2) If additional information is thereafter required, it shall be requested and provided pursuant to this subdivision, upon mutual agreement of the local agency and the claimant.

(3) The local agency's written response to the claim, as further documented, shall be submitted to the claimant within 30 days after receipt of the further documentation, or within a period of time no greater than that taken by the claimant in producing the additional information or requested documentation, whichever is greater.

(d) If the claimant disputes the local agency's written response, or the local agency fails to respond within the time prescribed, the claimant may so notify the local agency, in writing, either within 15 days of receipt of the local agency's response or within 15 days of the local agency's failure to respond within the time prescribed, respectively, and demand an informal conference to meet and confer for settlement of the issues in dispute. Upon a demand, the local agency shall schedule a meet and confer conference within 30 days for settlement of the dispute.

(e) Following the meet and confer conference the claim or any portion remains in dispute, the claimant may file a claim as provided in Chapter 1 (commencing with Section 900) and Chapter 2 (commencing with Section 910) of Part 3 of Division 3.6 of Title 1 of the Government Code. For purposes of those provisions, the running of the period of time within which a claim must be filed shall be tolled from the time the claimant submits his or her written claim pursuant to subdivision (a) until the time that claim is denied as a result of the meet and confer process, including any period of time utilized by the meet and confer process.

(f) This article does not apply to tort claims and nothing in this article is intended nor shall be construed to change the time periods for filing tort claims or actions specified by Chapter 1 (commencing with Section 900) and Chapter 2 (commencing with Section 910) of Part 3 of Division 3.6 of Title 1 of the Government Code.”

“**20104.4. Civil action procedures; mediation and arbitration; trial de novo; witnesses**

The following procedures are established for all civil actions filed to resolve claims subject to this article:

(a) Within 60 days, but no earlier than 30 days, following the filing or responsive pleadings, the court shall submit the matter to nonbinding mediation unless waives by mutual stipulation of both parties. The mediation process shall provide for the selection within 15 days by both parties of a disinterested third person as mediator, shall be commenced within 30 days of the submittal, and shall be concluded within 15 days from the commencement of the mediation unless a time requirement is extended upon a good cause showing to the court or by stipulation of both parties. If the parties fail to select a mediator within the 15-day period, any party may petition the court to appoint the mediator.

(b) (1) If the matter remains in dispute, the case shall be submitted to judicial arbitration pursuant to Chapter 2.5 (commencing with Section 1141.10) of Title 3 of Part 3 of the Code of Civil Procedure, notwithstanding Section 1141.11 of that code. The Civil Discovery Act (Title 4 (commencing with Section 2016.010), of the Code of Civil Procedure) shall apply to any proceeding brought under this subdivision consistent with the rules pertaining to judicial arbitration.

(2) Notwithstanding any other provision of law, upon stipulation of the parties, arbitrators appointed for purposes of this article shall be experienced in construction law, and, upon stipulation of the parties, mediators and arbitrators shall be paid necessary and reasonable hourly rates of pay not to exceed their customary rate, and such fees and expenses shall be paid equally by the parties, except in the case of arbitration where the arbitrator, for good cause, determines a different division. In no event shall these fees or expenses be paid by state or county funds.

(3) In addition to Chapter 2.5 (commencing with Section 1141.10) of Title 3 of Part 3 of the Code of Civil Procedure, any party who after receiving an arbitration award requests a trial de novo but does not obtain a more favorable judgment shall, in addition to payment of costs and fees under that chapter, pay the attorney's fees of the other party arising out of trial de novo.

(c) The court may, upon request by any party, order any witnesses to participate in the mediation or arbitration process.”

“**20104.6. Payment on undisputed portion of claim; interest on arbitration award or judgment**

(a) No local agency shall fail to pay money as to any portion of a claim which is undisputed except as otherwise provided in the contract.

(b) In any suit filed under Section 20104.4, the local agency shall pay interest at the legal rate on any arbitration award or judgment. The interest shall begin to accrue on the date the suit is filed in a court of law.”

**W. WORKING HOUR RESTRICTIONS:** Eight hours’ labor is a legal day’s work. Any workers time of service is restricted to eight hours during any calendar day and forty hours during any calendar week, unless overtime compensation is paid at not less than one and one-half times the basic rate of pay. The Contractor or Subcontractor shall, as a penalty to the District forfeit twenty-five dollars ($25) for each worker employed in the execution of the contract by the respective Contractor or subcontractor for each calendar day during which the worker is required or permitted to work more than eight hours in any one calendar day and forty hours in any one calendar week in violation of the law.

**X. EXAMINATION AND AUDIT**: All documents and records that relate in any way to this Agreement shall be maintained for a period of three years after the final payment under this Agreement. These records shall be subject to the examination and audit by the District and by the State Auditor, at the request of the District or as part of any audit of the District, for a period of three years after final payment under the Agreement.

**Y. DELAYS AND EXTENSIONS OF TIME**

6-4.4 Written Notice and Report. The first sentence of subsection 6-6.4 is hereby deleted and replaced with the following:

“If the Contractor desires payment for a delay as specified in Subsection 6-6.3 of the Standard Specifications, it shall notify the Engineer in writing within 3 days of the beginning of the delay. If the Contractor desires an extension of time as specified in Subsection 6-4.2 of the Standard Specifications, it shall notify the Engineer in writing within 3 days of the beginning of the delay. Such notice shall specify the nature of the delay, cause, and the conditions that set the beginning time for the delay.”

**Z. PROTECTION AND RESTORATION OF EXISTING IMPROVEMENTS**

The second paragraph of Subsection 400-1 of the Standard Specifications is hereby deleted and replaced with the following:

“The Contractor shall relocate, repair, replace, or reestablish all existing improvements within the project area which are not designated for removal (e.g., curbs, sidewalks, driveways, fences, walls, sprinkler systems, signs, utility installations, pavements, structures, etc.) which are damaged or removed as a result of his or her operations or as required by the Plans and Specifications.

Where existing traffic striping, pavement markings, and curb markings are damaged or their reflectivity reduced by the Contractor's operations, such striping or markings shall also be considered as existing improvements and the Contractor shall repaint or replace such improvements.

Relocations, repairs, replacements, or reestablishments shall be at least equal to the existing improvements and shall match such improvements in finish and dimensions unless otherwise specified.”

Subsection 400-1.1 of the Standard Specifications is hereby added to read as follows:

“All costs to the Contractor for protecting, removing, restoring, relocating, repairing, replacing, or reestablishing existing improvements shall be included in the unit cost for the various items of work and no additional compensation will be allowed therefore.”

**2. PUBLIC CONVENIENCE AND SAFETY**

**A. GENERAL:** In addition to the requirements specified in Part 6 of the Standard Specifications, traffic control shall conform to the provisions of the latest edition of the State of California, Department of Transportation, "Manual of Traffic Controls."

The Contractor shall give one week advance notice prior to the start of construction to all residences and businesses facing or siding on the construction area. Said notice shall be in writing on the Contractor's letterhead and shall explain in concise terms the extent and nature of the Work, the anticipated schedule, and office and emergency telephone numbers where the Contractor's representative can be reached.

Should the Contractor appear to be neglectful or negligent in furnishing warning and protective measures, the Engineer may direct attention to the existence of a hazard and the necessary warning and protective measures shall be furnished and installed immediately by the Contractor at his or her expense.

Should the Engineer point out the inadequacy of warning and protective measures, such action on the part of the Engineer shall not relieve the Contractor from responsibility for public safety or abrogate his or her obligation to furnish and pay for these devices.

If the Contractor cannot be contacted or if attention is directed to the existence of a hazard and the Contractor fails to provide the necessary safety devices, said devices will be placed, or caused to be placed, by the District. The cost of placement to these devices shall be the sole responsibility of the Contractor and shall be paid for at the rate of $50 per call-out plus $25 per traffic control device for each 24 hours, or fraction thereof, that the device is required. Said costs shall be deducted from the total contract price for the work.

Prior to beginning any construction, the Contractor shall furnish the Engineer with local emergency phone numbers where he or she or a representative may be contacted during non-working hours or days for the purpose of replacing or providing additional warning or safety devices as directed by the Engineer.

**B. UTILITIES:** It is anticipated that the existing utilities will not interfere with the Contractor's construction operations. However, the Contractor shall exercise due care to ensure that the utility facilities are not damaged during his or her operations, and must notify utilities and obtain an identification number before excavation or be subject to liability for damages to subsurface installations. When in doubt, the Contractor shall contact the utility concerned before proceeding further.

Upon completion of the project, the Contractor shall be responsible to remove all painted utility markings, whether done by him or her or the respective utility owners on behalf of the contractor for this project work, from the surfaces of sidewalks, driveway approaches, curbs and gutters using the removal method acceptable to the Engineer. Any damage to sidewalks, driveway approaches, curbs and gutters due to the Contractor’s removal operation shall be repaired at the Contractor’s expense and to the satisfaction of the Engineer. Payment for removing utility markings shall be included in other items of work, and no additional compensation will be allowed therefore.

**C. LOCATION:** The location and existence of any underground utility or substructure, if shown on Plans, was obtained from a search of available records. No guarantee is made or implied that the information is complete or accurate. It shall be the Contractor's responsibility alone to determine the exact location of underground utilities or substructures of every nature and to protect them from damage. The Contractor shall excavate and expose all high-risk underground facilities.

The Contractor shall notify the owners of all utilities and substructures as set forth in the General Provisions.

**D. RELOCATION**: The second sentence of the last paragraph of Subsection 402-4 of the Standard Specifications is hereby deleted and replaced with the following:

“When not otherwise required by the Plans and Specifications and when directed by the Engineer, the Contractor shall arrange for the relocation of service connections, as necessary, between the meter and property line, or between the meter and limits of construction.

The Contractor shall be compensated for the costs of locating and repairing, removing and relocating utility facilities, provided that any damage is not due to the failure of the Contractor or subcontractor to exercise reasonable care and the utility facilities were not indicated in the plans and specifications with reasonable accuracy. The Contractor shall not be assessed liquidated damages for delay in completion of the project, when such delay was caused by the failure of the District or the owner of the utility to provide for removal or relocation of such utility facilities.”

**E. DELAYS**: The second paragraph of Subsection 402-5 is hereby deleted and replaced with the following two paragraphs:

“The Contractor will not be entitled to damages or additional payment for delays attributable to utility relocations or alterations if correctly located, noted and completed in accordance with Subsection 402-1. The Contractor shall ascertain further detailed information to coordinate his or her work to this effect.

All notification of utility companies shall be by the Engineer based on Contractor's request as submitted to the Engineer at least 72 hours in advance of the needed work. Any costs for delay of the Contractor or utility companies in this regard shall be assigned to the Contractor, if these costs are a result of the Contractor's request being untimely in any respect, except for the utility company not responding at their agreed time.”

**F. AIR POLLUTION CONTROL**

Section 3-12.2, "Air Pollution", of the Standard Specifications is supplemented by the following:

“The Contractor shall comply with all air pollution control rules, regulations, ordinances and statutes which apply to any work performed pursuant to the contract including any air pollution control, rules, regulations, ordinances and statutes specified in Section 11017 of the Government Code.

In the absence of any applicable air pollution control rules, regulations, ordinances or statutes governing solvents, all solvents, including but not limited to the solvent portions of paints, thinners, curing compounds, and liquid asphalt used on the project shall comply with the applicable material requirements of the County Air Pollution Control District. All containers of paint, thinner, curing compound or liquid asphalt shall be labeled to indicate that the contents fully comply with said requirements.”

**G. WATER POLLUTION:** The Contractor shall comply with the requirements of Subsection 3-12.6 of the Standard Specifications and shall conduct his or her operations so as to prevent portland cement, mud, silt or other materials from entering the surface drainage structures of the adjoining street and any underground storm drainage system.

Full compensation for prevention of water pollution and all required control work for preservation, clean-up and restoration of damaged property shall be considered as included in the unit cost for the various contract items of work, and no additional compensation will be allowed therefor.

**H. PROJECT APPEARANCE:** The Contractor shall maintain a neat appearance to the work.

Full compensation for conforming to the provisions of this section not otherwise provided for shall be considered as included in unit cost for the various contract items of work involved and no additional compensation will be allowed therefor.

**I. WORK HOURS:** The Contractor's working hours shall be limited to the hours between 7:00 a.m. and 5:00 p.m., excluding recognized holidays. Deviation from normal working hours will not be allowed without prior consent of the District Engineer.

In the event work is allowed by the Engineer outside of the normal working hours, at the request of and for the benefit of the Contractor, inspection service fees may be levied against the Contractor at a rate of $50.00 per hour, including travel time where applicable. The above charge may also be levied if inspection services are deemed necessary by the Engineer as a matter of public safety or to otherwise insure the quality of the work.

**J. CONSTRUCTION YARD:** It shall be the Contractor's responsibility to locate any storage sites for materials and equipment needed and such sites must be approved in advance by the Engineer and must be free of objectionable material. The Contractor must submit to the Engineer for approval any and all agreement(s) between the Contractor and the property owner(s) of said storage site(s) and/or construction site(s) for approval prior to the start of construction. Said agreement(s) must provide for the restoration of the site(s) by the Contractor prior to the filing of "Notice of Completion" by the Engineer. Full compensation shall be considered as included in unit cost for the various contract items of work involved and no additional compensation will be allowed therefor.

No equipment or material used for staging shall be allowed to be stored on any District property or city streets during non-work time. All stage equipment and/or material shall be stored offsite and if such location is used, it shall be submitted in writing and approved by the District Engineer. All costs associated with such staging and location shall be included in other bid items of work and no additional compensation will be allowed thereof.

**K. SANITARY CONVENIENCE:** Necessary sanitary facilities for the use of the workmen performing the work, properly secluded from public observation and in compliance with health ordinances and laws, shall be constructed and maintained by Contractor, in a manner approved by the Engineer, and the use of such facilities shall by strictly enforced by the Contractor.

**L. INSPECTION:** The Engineer, or his or her authorized agent, shall at all times have access to work during construction and shall be furnished, to the extent possible, complete information and all documentation to ascertain full knowledge regarding the progress, workmanship and character of materials used and employed in the work. Whenever required, the Contractor shall furnish to the District for test, and free of charge, samples of any one of the materials proposed to be used in the work. Said samples shall be delivered by the Contractor at the place within the District designated by the Engineer. Rejected material must be immediately removed from the work by the Contractor and shall not again be brought back to the site of the improvement.

The Contractor shall notify the Engineer or his or her authorized agent forty-eight (48) hours in advance when he or she will require inspection for either material or work to be done.

The inspection of the work shall not relieve the Contractor of any of his or her obligations to fulfill the contract as prescribed. Defective work shall be made good, and unsuitable materials may be rejected, notwithstanding the fact that such defective work and unsuitable materials have been previously overlooked by the Engineer or his or her authorized agent and accepted or estimated for payment.

**M. RESPONSIBILITY OF THE DISTRICT:** The District shall not be held responsible for the care or protection of any material or parts of the work prior to final acceptance, except as expressly provided for in these Contract Documents.

**N. RECYCLING OF MATERIALS:** Contractor's Obligation. Recycling of asphalt concrete, portland cement concrete, aggregate base, and green waste (trees and shrubs) is required. The Contractor is required to recycle at least 50% of all recyclable materials. All recycled materials shall be weighed on a certified weigh scale with weight tickets showing project name. RECORDS OF DISPOSAL, INCLUDING WEIGHT OF MATERIALS, SHALL BE SUBMITTED TO THE DISTRICT ON A MONTHLY BASIS.

Prior to commencing work, the Contractor shall complete the "Construction and Demolition Waste Reduction and Recycling Plan" form and submit it to the Parks Department for review and approval. The Contractor will be expected to follow the approved Plan and document results during construction. At the completion of activities, the Contractor shall submit the "Construction and Demolition Waste Reduction and Recycling Report" form to the Public Works Department for review and approval of compliance with the Plans. The above-referenced forms are provided in Appendix 2.

The Contractor is obligated, under this contract, to recycle the waste material through an approved recycling plant. **In the event the Contractor fails to comply with the C&D requirements (at least 50%), three percent (3%) of the approved contract amount will be forfeited to the District by Contractor as a penalty.**

Payment for Recycling of Materials shall be included in the unit cost for the various contract items of work and no additional compensation will be allowed therefor.

O. TRAFFIC AND ACCESS: *The Contractor shall notify the occupants of all affected properties at least 48 hours prior to any temporary obstruction of access. Vehicular access to property line shall be maintained, except as required for construction for a reasonable period of time. No overnight closure of any driveway will be allowed, except as permitted by the Engineer. Temporary ramps for driveways shall be provided and maintained by the end of each working day and during the weekends. Temporary driveway ramps shall be constructed with crushed miscellaneous base as directed by the Engineer.*

Contractor shall maintain vehicular, bicycle, and pedestrian traffic access through the project area at all times. A minimum of one 12-foot wide traffic lane and a minimum of one 4-foot wide all-weather paved pedestrian walkway shall be provided at all times, except as permitted by the Engineer. During times when less than 2 lanes of traffic are provided, contractor shall provide traffic control for the entire duration there is less than 2 lanes. The traffic lanes shall be maintained on all-weather pavement and shall remain unobstructed.

**P. STREET CLOSURES, DETOURS, BARRICADES, PARKING:** Street closures will not be allowed, except as specifically permitted by the Engineer.

The Contractor shall prepare any traffic control or detour plans that may be required as directed by the Engineer.

Lane transitions shall conform to the Caltrans Traffic Manual, Section 5-08.4, “Transition Area.”

Temporary traffic channelization shall be accomplished with delineators. Temporary striping will not be allowed unless specifically permitted by the Engineer. The Contractor shall prepare any plans that may be required for temporary striping to the satisfaction of the Engineer. In no event will temporary striping be allowed on finished pavement surfaces which are to remain.

The Contractor shall schedule an employee to police the temporary delineators and barricades within the travel way during weekday, nonworking hours and over Saturdays, Sundays, and holidays. Any corrective work required to be done by District forces shall be back charged to the Contractor based on the actual costs, plus District overhead and withheld from the final payment.

As specified in the General Provisions, the schedule shall be submitted to the Engineer for approval prior to commencing work. This schedule shall allow affected people ample “on-street” parking within a reasonable distance from their homes and businesses. Requests for changes in the schedule shall be made in accordance with the General Provisions.

Temporary “No Parking” signs shall be posted at least 24 hours, but no more than 48 hours, in advance of the work. The signs shall be placed no more than 250 feet apart on each side of the street and at shorter intervals if conditions warrant. Signs shall be posted only for the areas necessary to accomplish the work. The Contractor shall provide the signs and will be responsible for adding the dates and hours of closure to the signs, removal of the signs, and furnishing and placing of barricades, if necessary, for posting of signs. All signs shall be removed within 48 hours after the effective date.

Payment for STREET CLOSURES, DETOURS, BARRICADES, PARKING shall be considered as included in the unit cost for bid item: “Traffic Control” no additional compensation will be allowed therefor.

**TECHNICAL PROVISIONS**

**PLEASANT VALLEY RECREATION & PARK DISTRICT**

**PV POOL DECK RESURFACING PROJECT**

**SPEC NO. PVPD23-24**

**THE PRODUCT:** Liquid-applied polyurethane waterproofing coating on ICC rating on deck surfaces.

1. The waterproofing coating system:
   1. Is seamless;
   2. Fully bonds to substrates both adhesively and mechanically;
2. Can be applied to OSB or plywood and metal substrates;
3. Can be used in a broad variety of exposed conditions such as balconies, pedestrian bridge decks, observation decks and roof decks.
4. Is fast curing.
5. Meets California VOC and SCAQMD Requirements

**COORDINATION:** Section 07180 defines requirements for the liquid applied polyurethane waterproofing coating system itself. It is important to define certain substrate requirements and requirements of adjacent trades in pertinent other sections of your specification as follows:

1. Section 03300 - Cast-in-place concrete:
2. Concrete that is substrate to the coating system should have a finish equal to light steel troweling followed by a fine hair broom.
3. An appropriate wet curing procedure should be used on the concrete.
4. Control joints in the concrete, if required, should be in accordance with pertinent ACI and PCA standards.
5. Drain flanges at coating level should be integrally cast into, and be flush with, concrete deck surfaces that slope to drain..
6. Section 06125 - Plywood decking:
   1. Plywood that is substrate to the waterproofing coating system must be exterior grade minimum 5/8" thick with A-side up, fastened with ring-shank nails, blocked under every joint unless it is tongue-and-groove minimum 1-1/8" thick.
   2. Deck surfaces should slope to drain.
   3. Deck drains must have flanges at the coating level that are flush with the deck surface.
   4. Particle boards are not suitable substrates.
7. Section 07600 - Flashing and sheet metal:
   1. Metal flashings that are substrate to the waterproofing coating system should be a minimum of 24 gage aluminum, copper, galvanized, or stainless steel.
   2. Set metal flashings in continuous bedding bead of hybrid sealant installing sealant S-bead between metal laps and mechanically fastening to substrate along leading edges at every 4" on center, staggered linearly, to lay flat and without fishmouths.

END OF COVER PAGE(s)

PART 1 GENERAL

* 1. SUMMARY
     1. Section includes: Provide a complete polyurethane waterproofing coating system where indicated on the Drawings, including all applicable sealants and elastomeric flashings needed to ensure a complete waterproof and weathertight system for deck, ramp, stair and landing surfaces at locations indicated.
     2. Related work:
        1. Documents affecting work of this Section include, but are not necessarily limited to, General Conditions, Supplementary Conditions, and Sections in Division 1 of these Specifications.
  2. SUBMITTALS
     1. Comply with pertinent provisions of Section 01330.
     2. Product data:
        1. Materials list of items proposed to be provided under this Section.
        2. Manufacturer's specifications and other data needed to prove compliance with the specified requirements.
        3. Shop Drawings or catalog illustrations in sufficient detail to show installation and interface of the work of this Section with the work of adjacent trades.
        4. Manufacturer's current recommended installation procedures which, when reviewed by Architect, will become the basis for accepting or rejecting actual installation procedures used on the Work.
        5. Written documentation of applicator's qualifications, including reference projects of similar scope and complexity, with current phone contacts of architects and owners for verification.
  3. QUALITY ASSURANCE
     1. Use adequate numbers of skilled workmen thoroughly trained and experienced in the necessary crafts and completely familiar with the specified requirements and methods needed for proper performance of the work of this Section.
     2. Applicator qualifications:
        1. Applicator shall have at least three years experience in installing materials of types specified and shall have successfully completed at least three projects of similar scope and complexity.
        2. Applicator shall designate a single individual as project foreman who shall be always on site during installation.
     3. Convene a pre-installation job-site conference four weeks prior to commencing work of this Section:
        1. Secure attendance by Architect, Contractor, applicator, and authorized representatives of the coating system manufacturer and interfacing trades.
        2. Examine Drawings and Specifications affecting work of this Section, verify all conditions, review installation procedures, and coordinate scheduling with interfacing portions of the Work.
  4. DELIVERY, STORAGE AND HANDLING
     1. Deliver materials to job site in manufacturer's unopened containers with all labels intact and legible at time of use.
     2. Maintain the products in accord with manufacturer's recommendations with proper precautions to ensure fitness of material when installed.
     3. Comply with pertinent provisions of Section 01660.
  5. SUBSTRATE CONDITIONS
     1. General:
        1. Provide applicator with surfaces that are broom clean, dry, sound and free of protrusions, excessive roughness, foreign matter, frost, ice and other contaminants which may inhibit application or performance of the waterproofing coating system.
        2. Using suitable abrasive methods, remove residue of form release, curing compound, chemical retarders and other surface treatments, laitance, mortar smear, saw cutting residue, mill scale, rust, loose material and other contaminants from concrete, masonry and ferrous metal surfaces to receive the work of this Section.

1. Concrete Where work of this Section will be applied to 14-28 day cured concrete and a minimum of 3,500 psi compressive strength
2. Decks:
   1. Slope deck surfaces to drains that have flanges at coating level which are flush with deck surfaces.
   2. Rigidly install pipe, vents, and other surface protrusions, properly flash them, and cover to prevent entry of coating materials.
3. Metal flashings: Where metal flashings are substrate to waterproofing coating, set the flashings in continuous bedding bead of hybrid PolyTuff sealant; install sealant S-bead between metal laps and mechanically fasten to substrate along leading edges at every 4" on center, staggered linearly, to lay flat without fish mouths. Metal flashings shall be taped with polyester woven fabric with hotmelt acrylic pressure sensitive adhesive.
4. Joints: Configuration shall be consistent with this Section and with all other requirements of the Contract Documents.
   1. WARRANTY
      1. Deliver to the Architect signed copies of the following written warranties against defective materials and workmanship for a period of two years following date of completion. Warrant that installed waterproof coating system shall be free of defects including adhesive failure, cohesive failure, weathering deficiencies and waterproofing failure resulting from substrate cracking up to 1/16 inch.
         1. Manufacturer's material ten (10) year warranty covering materials.
         2. Applicator's standard warranty covering workmanship.

PART 2 PRODUCTS

* + - * 1. GENERAL

Provide a complete liquid applied polyurethane waterproofing coating system having the following minimum attributes:

System designed for waterproofing decks utilizing metal lath and plywood subject to pedestrian traffic.

Complying with a Class A fire rating on plywood substrates.

Color to be selected by Architect from manufacturer's standard color range.

Acceptable products:

PSI P-Tuff Classic Base or E-Tuff 100 Base Membrane

PSI Topshield EST-FR (SC)

PSI Topshield EST (SC)

* + - * 1. ACCESSORIES

Primer: As recommended by coating system manufacturer.

Joint backing: Closed-cell, polyethylene rod as recommended by coating manufacturer.

Aggregate: 12-20 mesh silica sand, or EPDM rubber aggregate approved by coating manufacturer

Sealants

PTS E-101 Joint Sealant

P-Tuff Classic

* + - * 1. OTHER MATERIALS

Provide other materials, not specifically described but required for a complete and proper installation, as selected by the Contractor and approved by the coating system manufacturer as compatible, subject to review of the Architect.

PART 3 EXECUTION

* 1. SURFACE CONDITIONS
     1. Coordinate as required with other trades to assure proper and adequate provision in the work of those trades for interface with the work of this Section.
     2. Applicator shall examine the areas and conditions under which work of this Section will be performed.
        1. Verify conformance with manufacturer's requirements;
        2. Report unsatisfactory conditions in writing to the Architect;
        3. Do not proceed until unsatisfactory conditions are corrected.
  2. PREPARATION
     1. Surface preparation and detailing procedures to be in accord with waterproof coating system manufacturer's instructions and recommendations except where more stringent requirements are indicated.
     2. Clean all deck surfaces to receive coating system in accord with manufacturer's instructions; vacuum clean or blow clean with oil-free compressed air all surfaces to receive sealants, detailing materials or coatings immediately prior to installation.
     3. Rout, clean, prepare and detail surfaces in accord with manufacturer's instructions
     4. Clean metal surfaces to bright metal by mechanically abrading with an angle grinder and wire brush cup or mechanical etching or ; scuff-sand lead flashing and plastic surfaces.
     5. Prime surfaces in accord with manufacturer's instructions.
     6. Install E-Tuff or P-Tuff Classic mixed material at corner of all horizontal-to-vertical junctures subject to movement and cover with 1" detail cant of approved sealant; install 1" detail cants at projections, curbs and other horizontal-to-vertical junctures.
     7. Install detail coats, joint and crack treatments, and liquid flashings in accord with manufacturer's instructions.
     8. Allow detail applications to cure in accord with manufacturer's instructions prior to general application of coating.
  3. APPLICATION
     1. Install waterproof coating system in accord with manufacturer's recommendations and instructions as applies to the Work except where more stringent requirements are indicated.
        1. Grid deck surfaces to assure proper coverage rates and verify coating wet-film mil thickness with gauges as work progresses.
        2. Retain empty product containers during course of work to aid in determining whether completed coating system complies with manufacturers average thickness requirements.
     2. Verify proper dry condition of substrate using method recommended by coating system. manufacturer; perform adhesion checks prior to general application of coating system using field adhesion test method recommended by manufacturer.
     3. Mask off adjoining surfaces not to receive coating system.
     4. Wipe clean all detail coats with white rags wetted with Xylene solvent; do not saturate detail coat.
     5. Apply coating base coat uniformly and allow to cure in accord with manufacturer's instructions.
     6. Feather edge when entire area cannot be completed in one day; clean area 6" wide along edge of coating with Xylene solvent on clean white rags prior to startup on next working day; use interlaminary primer per manufacturer's instructions as needed; overlap existing work by 6" with new work.
     7. Apply coating system finish coats in accord with manufacturer's instructions.
        1. Immediately broadcast aggregate into wet material at rate recommended by manufacturer and backroll to evenly distribute and totally encapsulate.
        2. Allow to cure per manufacturer's instructions.
  4. PROTECTION AND CLEAN-UP
     1. Promptly remove primer or coating material from adjacent surfaces with MEK, Toluene or Xylene; leave work area in broom clean condition.
     2. Allow completed Work to cure 24 hours before opening to pedestrian traffic.

END OF SECTION

APPENDIX A

**CONSTRUCTION DRAWINGS**